## KNM
Prepared by: | Kavitha
Report Date | 2021-11-11
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94923 | 20-10-2021 | Al windows | Estimate to be prepared
94945 | 2021-11-03 | Tan brown granite | 82479
94942 | 2021-11-03 | Pendrive | Online purchase
94941 | 2021-11-02 | Cement | 82386
94940 | 2021-11-02 | Shabad stone | Estimate to be prepared
List of requisitions Where PO/WO is prepared and items have not received at site
94939 | 2021-11-01 | Solid blocks | Follow up with suppleir
94929 | 22-10-2021 | Bathroom tiles | Partly delivered
94928 | 20-10-2021 | Door beeding nails | Follow up with suppleir
94927 | 20-10-2021 | Screws | Follow up with suppleir
94924 | 20-10-2021 | MS railing | pick up from SSLLP
94919 | 20-10-2021 | Al windows | Partly delivered
94916 | 20-10-2021 | False ceiling | Follow up with suppleir
94914 | 20-10-2021 | electrical wires | Partly delivered
94909 | 2021-10-12 | GI Clamps | Follow up with suppleir
94907 | 2021-10-12 | PVC Pipes | Partly delivered
94904 | 2021-10-11 | Flat files | Follow up with suppleir
94902 | 2021-10-09 | Templates | Follow up with suppleir