## KNM
Prepared by: | Kavitha
Report Date | 2021-11-03
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100542 | 27-10-2021 | Tan brown granite | 82247
List of requisitions Where PO/WO is prepared and items have not received at site
100543 | 27-10-2021 | Manhole covers | follow up with supplier
100537 | 20-10-2021 | curb stone | follow up with supplier
100524 | 2021-10-09 | PVC bends | pick up from ssllp
10052 | 2021-10-08 | Hanging light | follow up with supplier
100521 | 2021-10-08 | LED ceiling lights | partly delivered
100514 | 2021-10-06 | SS name plates | follow up with supplier
100513 | 2021-10-06 | SS name plate vowel shape | follow up with supplier
100508 | 2021-10-05 | MS round pipe | partly delivered
100505 | 29-09-2021 | Solid blocks | partly delivered from ssllp
100490 | 18-09-2021 | MI cemeras | follow up with supplier
100484 | 14-09-2021 | MS Window grills | pick up from ssllp