## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estaes
Site: |  | 2021-11-20
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
175429 | 2021-11-15 | Raisers, Frames | PO 82827
175430 | 2021-11-15 | Travertine Carolina | PO 82916
175431 | 2021-11-15 | Cannon camera | Online purchase
175432 | 2021-11-15 | Urban wood natural tiles | PO 82912
175433 | 2021-11-17 | Electrical wires | PO 82839
175435 | 2021-11-17 | Gate Lights | PO 82841
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175325 | 2021-07-20 | Solar Module | Work under process
175411 | 2021-10-30 | Steel grey granite | Collect from SOVLLP
175413 | 2021-11-02 | Mortise lock | Stock to be receive from supplier.
175416 | 2021-11-02 | Sanitary | Deliverd
175422 | 2021-11-05 | MS Gate | Fabrication under process
175426 | 2021-11-09 | Mortise lock | Stock to be receive from supplier.