## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-11-13
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing8mm | Requisition not found in email send it again
177937 | 20.08.2021 | Swimming pool Equipments Supply | WO is completed in word format, kindly delete from
177995 | 15.09.2021 | Camera | Online purchase
178111 | 20.10.2021 | Lawn Mover | PO 81981
178125 | 29.10.2021 | Wall Mixture | Rates to be finalize by MD
178126 | 29.10.2021 | Wall Mixture | Rates to be finalize by MD
178127 | 29.10.2021 | Wall hung WC | Rates to be finalize by MD
178128 | 29.10.2021 | Wall Hung WC | Rates to be finalize by MD
178147 | 06.11.2021 | Kitchen sets | PO 82799
178148 | 08.11.2021 | Cutter pumps | PO to be issue
178165 | 13.11.2021 | Panel doors | PO 82909, 82910
178167 | 15.11.2021 | MS Square pipe 1 mm | PO 82805
178168 | 16.11.2021 | 8 & 6 model metal boxes | PO 82778
178170 | 17.11.2021 | Cutter Pumps | PO to be issue
178171 | 17.11.2021 | De-watering pumps | PO to be issue
178172 | 17.11.2021 | MS Square Pipe 1.5mm | PO 82806
178173 | 17.11.2021 | Fruit Packing cover | PO 82779
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177152 | 26.11.2020 | Passenger lift& Sevice lift | Work under Progress
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 2 | Half of the material we received remaining supplier arrange the material delivered by next week
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Partially delivered
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177498 | 19.03.2021 | Stainless steel sink | Partially delivered
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Supplier Arrange the Material Delivered by Next week
177562 | 06.04.2021 | Vertrified tiles | Supplier Arrange the Material Delivered by Next week
177844 | 23.07.2021 | Rain water line MS pipe | Under fabrication
177896 | 07.08.2021 | Vertrified tiles ,beige,Grigio,urban wood | Half of the Material is ready we will pick up from GMR
177901 | 07.08.2021 | Urban wood natural, | Half of material we received remaining we will pick up from GMR
178013 | 21.09.2021 | Tiles urbanwood natural,Crema Marfil | Half of material we received remaining we will pick up from GMR
178050 | 04.10.2021 | AMF panel | Material to be received from supplier
178058 | 05.10.2021 | Tan Brown Granite | Supplier Arrange the Material Delivered by Next week
178093 | 12.10.2021 | Tandoor stone | Supplier Arrange the Material Delivered by Next week
178112 | 20.10.2021 | Garbage Bin | Deliverd
178133 | 01.11.2021 | Sadar ali Grey | Pick up from SOV
178137 | 03.11.2021 | PVC false ceiling | Material is ready ,But Payment not done
178138 | 03.11.2021 | Flush door ,Cylindrical Locks | Collect from SSLLP
178139 | 03.11.2021 | Indigo paint | Deliverd
178140 | 05.11.2021 | Ms round pipe | No stock At supplier
178143 | 05.11.2021 | LED lights | Half Of the mateial is Received ,Remaining Supplier arrange the material
178144 | 06.11.2021 | MS box pipe | Supplier Arrange the Material Delivered by Next week
178151 | 08.11.2021 | Pressure gauge | Deliverd
178152 | 08.11.2021 | Regal beige,Urban wood natural Crema marfil | Half of material we received remaining we will pick up from GMR.
178155 | 09.11.2021 | SS Screws | Deliverd
178156 | 09.11.2021 | Part 2 Grills | Material under fabrication
178157 | 09.11.2021 | Part 2 Grills | Material under fabrication
178158 | 09.11.2021 | Part 2 Grills | Material under fabrication
178162 | 12.11.2021 | Country rosso,Country Black.Pacific blue | Collect from SSLLP
178164 | 13.11.2021 | Roff chemical liquid , Janathapaste | Deliverd
178166 | 15.11.2021 | Carpet Grass | Supplier Arrange the Material Delivered by Next week