## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-10-30
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
164089 | 2021-10-30 | Wipro Led Lights | Cancelled due to specifications are incorrect
164145 | 2021-11-15 | Flat files | Follow up with admin
164146 | 2021-11-16 | Luminoius tape | Local Purchase
164147 | 2021-11-16 | Orange jackets | Cancelled due to specifications are incorrect
164149 | 2021-11-17 | Salwood doors | Requisition not found in email send it again
164150 | 2021-11-17 | EWC | Requisition not found in email send it again
164155 | 2021-11-18 | Bolts | Requisition not found in email send it again
164157 | 2021-11-18 | Sanitary material | Requisition not found in email send it again
164160 | 2021-11-19 | Electrical material | PO 82883, 82885
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163601 | 2021-06-30 | HT Works | Call supplier for completion of work
163662 | 2021-07-27 | LT Panels | Part metrail received balance to be receive
163704 | 2021-08-07 | ACP Cladding | Work under process
163797 | 2021-11-03 | UPS | Work under process
163889 | 2021-09-23 | Fire safety equipments | Work under process
163984 | 2021-10-06 | PVC False ceiling material | Material deliverd, work under process
164011 | 2021-10-18 | Busduct material | WO issued, work under process
164046 | 2021-11-20 | Fosroc loxfix P | Deliverd
164078 | 2021-10-27 | Plumbing material | Coordinate with SFS Hardware for material delivery
164103 | 2021-11-03 | Electrical items | Work under process
164116 | 2021-11-06 | MS Rolling shutter | Material deliverd, work under process
164090 | 2021-10-30 | AL Ladder | Coordinate with Aluminium center Pvt ltd, for material delivery
164125 | 2021-11-10 | Sadwitch panel with PU Foam | Rate to be finalize by MD
164101 | 2021-11-02 | FRP Pipes | Deliverd
164124 | 2021-11-10 | Line dori | Deliverd
164126 | 2021-11-10 | Fire steel doors | Materil will be deliverd after payment
164127 | 2021-11-11 | Roff stone tiles adhesives | Deliverd
164128 | 2021-11-10 | C-Channel | Deliverd
164131 | 2021-11-11 | L Angle | Deliverd
164142 | 2021-11-13 | Sintex tank | Supplier will deliver, co ordinate with him
164148 | 2021-11-17 | Battery charger | Co ordinate with sanjay technical