## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-10-30
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180835 | 2021-07-29 | UPVC Track sliding windows | Deliverd
180869 | 2021-09-15 | UPVC Track sliding windows | Under fabricaion
180886 | 2021-10-28 | Saniatry Material | Part material deliverd, balance can be picked up from SSLLP
180887 | 2021-10-28 | Wifi security cameras | Advance payment is under process
180892 | 2021-11-10 | CP Fittings | Deliverd
180893 | 2021-11-12 | EWC Flush tanks | Pick up from SSLLP