## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Heights
Site: |  | 2021-10-30
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
181754 | 2021-11-17 | MS Tools | PO 82864
181755 | 2021-11-17 | Rod cutting blade | PO 82840
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181736 | 2021-10-13 | Hand pulling trolley | Collect from supplier
181748 | 2021-11-08 | Rod cutting machine | Collect from supplier
181750 | 2021-11-11 | MS Round pipe | Collect from supplier
181752 | 2021-11-17 | Curing pipe | Pick up from SSLLP
181753 | 2021-11-17 | Wooden thadkas | Collect from supplier