## KNM
Prepared by: | Kavitha
Report Date | 18-11-2021
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94951 | 2021-11-12 | Tan brown granite | 82761
94948 | 2021-11-12 | LED street lights | 82620
94923 | 20-10-2021 | AL Windoes | rates to finalize
94960 | 17-11-2021 | Tan brown granite | 82870
94953 | 13-11-2021 | shabad stone | 82760
List of requisitions Where PO/WO is prepared and items have not received at site
94928 | 20-10-2021 | Door beeding nails | Follow up with suppleir
94927 | 20-10-2021 | Screws | Follow up with suppleir
94924 | 20-10-2021 | MS railing | pick up from SSLLP
94919 | 20-10-2021 | Al windows | Partly delivered
94916 | 20-10-2021 | False ceiling | Follow up with suppleir
94909 | 2021-10-12 | GI Clamps | Follow up with suppleir
94907 | 2021-10-12 | PVC Pipes | Partly delivered
94904 | 2021-10-11 | Flat files | Follow up with suppleir
94902 | 2021-10-09 | Templates | Follow up with suppleir
94946 | 2021-11-05 | gardening material | Follow up with suppleir
94945 | 2021-11-03 | tanbrown granite | pick up from SSLLP
94940 | 2021-11-02 | shabad stone | pick up from SSLLP
94921 | 20-10-2021 | doors | pick up from SSLLP
94959 | 17-11-2021 | Vetrigied tiles | pick up from SSLLP
94958 | 17-11-2021 | utility dado | pick up from SSLLP
94957 | 17-11-2021 | measuring tapes | pick up from SSLLP
94956 | 17-11-2021 | water bubbles | pick up from SSLLP
94955 | 16-11-2021 | bamboo jadu | pick up from SSLLP
94954 | 13-11-2021 | coconut brooms | pick up from SSLLP