## KNM
Prepared by: | Kavitha
Report Date | 25-11-2021
Site | GVDC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
13325 | 13-08-2021 | Tp link router with sim card | Online purchase
13382 | 19-10-2021 | Extended gate mesh | PO to be issue
13404 | 2021-11-11 | FRP Pipes | 82632
13406 | 2021-11-12 | CPVC Material | 82651, 82812, 82816
List of requisitions Where PO/WO is prepared and items have not received at site
13356 | 20-09-2021 | RMC | pick up from supplier
13345 | 2021-03-09 | RO Plant | pick up from supplier
13375 | 2021-10-14 | wheel barroww with rubber wheels | pick up from supplier
13367 | 2021-10-09 | Lawn mover | pick up from supplier
13400 | 2021-11-01 | recron bags | pick up from SSLLP
13401 | 2021-11-01 | cofee powder | pick up from supplier
13402 | 2021-11-01 | recron bags | pick up from SSLLP
13405 | 2021-12-11 | ceiling rans | pick up from supplier