## KNM
Prepared by: | Kavitha
Report Date | 25-11-2021
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100550 | 2021-11-09 | Iron brush | cancelled
100553 | 16-11-2021 | Manhole covers | 82834
List of requisitions Where PO/WO is prepared and items have not received at site
100552 | 2021-11-12 | switches | pick up from ssllp
100549 | 2021-11-06 | waystrips connectors | follow up with supplier
100548 | 2021-11-05 | shabad stone | follow up with supplier
100547 | 2021-11-05 | flush doors | follow up with supplier
100546 | 2021-11-03 | cp fittings | pick up from ssllp
100545 | 2021-11-03 | sanitary | pick up from ssllp
100537 | 20-0-2021 | curb stone | follow up with supplier
100521 | 2021-10-08 | led ceiling lights | partly delivered
100514 | 2021-10-06 | ss name plates | follow up with supplier
100513 | 2021-10-06 | ss name plate vowel shape | follow up with supplier