## KNM
Prepared by: | Kavitha
Report Date | 2021-12-03
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94972 | 26-11-2021 | Vertified Tiles | Sent to MD's approval
94971 | 26-11-2021 | utility dado | Sent to MD's approval
94970 | 26-11-2021 | Vertified Tiles | Sent to MD's approval
94969 | 25-11-2021 | Electrical wires | Po issued- Po no-83048
94963 | 22-11-2021 | Wifi Router | Online purchase
94923 | 20-10-2021 | AL Windows | Rates to be finilize
List of requisitions Where PO/WO is prepared and items have not received at site
94928 | 20-10-2021 | Door beeding nails | Follow up with suppleir
94927 | 20-10-2021 | Screws | Follow up with suppleir
94924 | 20-10-2021 | MS railing | pick up from SSLLP
94919 | 20-10-2021 | Al windows | Partly delivered , remaining to be collecte from SSLLP
94916 | 20-10-2021 | False ceiling | Follow up with suppleir
94907 | 2021-10-12 | PVC Pipes | Partly delivered, remaining to be collect from SSLLP
94904 | 2021-10-11 | Flat files | Follow up with suppleir
94902 | 2021-10-09 | Templates | Follow up with suppleir
94946 | 2021-11-05 | gardening material | Follow up with suppleir
94940 | 2021-11-02 | shabad stone | pick up from SSLLP
94921 | 20-10-2021 | doors | pick up from SSLLP
94959 | 17-11-2021 | Vetrigied tiles | pick up from SSLLP
94958 | 17-11-2021 | utility dado | pick up from SSLLP
94968 | 25-11-2021 | Green hose pipe | pick up from SSLLP
94967 | 25-11-2021 | Roff chemical | Follow up with suppleir