## KNM
Prepared by: | Kavitha
Report Date | 2021-12-03
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100559 | 26-11-2021 | sanitary | Po issued--Po no-83058
100558 | 26-11-2021 | cp fittings | Po issued--Po no-83060
100557 | 25-11-2021 | Electrical wires | Po issued--Po no-83047
100556 | 25-11-2021 | Electrical items | Po issued--Po no-83041, 83044, 83010
100555 | 25-11-2021 | Electrical wires | Po issued--Po no-83045
List of requisitions Where PO/WO is prepared and items have not received at site
100554 | 19-11-2021 | MS Section | follow up with supplier
100553 | 16-11-2021 | Manhole Covers | follow up with supplier
100547 | 2021-11-05 | flush doors | follow up with supplier
100546 | 2021-11-03 | cp fittings | Partly delivered, balance to be collect from SSLLP
100537 | 20-0-2021 | curb stone | follow up with supplier
100521 | 2021-10-08 | led ceiling lights | Partly delivered, balance to be collect from SSLLP
100514 | 2021-10-06 | ss name plates | follow up with supplier
100513 | 2021-10-06 | ss name plate vowel shape | follow up with supplier