## KNM
Prepared by: | Kavitha
Report Date | 2021-12-09
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100563 | 2021-12-01 | Letter Box | Estimate to be prepared
List of requisitions Where PO/WO is prepared and items have not received at site
100567 | 2021-02-12 | 3 core copper wire | follow up with supplier
100566 | 2021-12-02 | BT patching material | Pick up from SSLLP
100562 | 29-11-2021 | Sanitary items | Pick up from SSLLP
100561 | 29-11-2021 | cp fittings | Pick up from SSLLP
100558 | 26-11-2021 | cp fittings | Partly delivered, balance to be collect from SSLLP
100537 | 20-0-2021 | curb stone | follow up with supplier
100521 | 2021-10-08 | led ceiling lights | Partly delivered, balance to be collect from SSLLP
100546 | 2021-11-03 | cp fittings | Partly delivered, balance to be collect from SSLLP