## VOC LLP
Prepared by: | Mounika
Report Date | 04.12.21
Site | Villa Orchids LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
63806 | 18.11.21 | CC Camera's | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
63807 | 27.11.21 | Sintex water tank | Pick from SSLLP