## KNM
Prepared by: | Kavitha
Report Date | 15-12-2021
Site | GVDC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
13422 | 13-08-2021 | Tp link router with sim card | Online purchase
13382 | 19-10-2021 | Extended gate mesh | Sample to be sent to MD Sir
13413 | 22-11-2021 | Biometric machine adaptor | Online purchase
List of requisitions Where PO/WO is prepared and items have not received at site
13345 | 2021-03-09 | RO Plant | work under process
13375 | 14-10-2021 | Wheel barrow with rubber wheels | follow up with supplier
13401 | 2021-01-11 | coffe powder | follow up with supplier
13418 | 26-11-2021 | recron packets | follow up with supplier
13416 | 26-11-2021 | LED lights | follow up with supplier
13406 | 2021-12-11 | CPVC Material | follow up with supplier