## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-12-18
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
164032 | 2021-10-19 | Landline phone | PO 83814
164173 | 2021-11-22 | FRP Manholes | Samples to get from suppliers
164208 | 2021-11-29 | Mi cc cameras, wifi routers | PO 83820, Mi cameras are yet to be receive
164216 | 2021-11-30 | GI Cable tray ladder type | PO 83209
164231 | 2021-12-02 | Smart TV | Online purchase
164249 | 2021-12-06 | Split AC | Qty included in the other PO
164256 | 2021-12-08 | L Patti, SS Screws | PO 83549, 83612
164262 | 2021-12-08 | Split AC | PO 83778
164263 | 2021-12-08 | Organic waste converter | Quotes to be receive by likitha
164264 | 2021-12-08 | Digital energy meter | Quotes to be receive by likitha
164265 | 2021-12-08 | Electromegnetic flow meter | Quotes to be receive by likitha
164295 | 2021-12-13 | Coper armourd cable | Local purchase by waseem
164297 | 2021-12-13 | Lenovo laptop charger | Online purchase by sunil
164299 | 2021-12-15 | 185 sqmm copper multi standerd felxible | Cancelled by site
164301 | 2021-12-15 | Calm shell cards | Online purchase a waiting for delivery
164303 | 2021-12-18 | RMC | PO 83837
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163601 | 2021-06-30 | HT Works | Call supplier for completion of work
163704 | 2021-08-07 | ACP Cladding | Work under process
163889 | 2021-09-23 | Fire safety equipments | Work under process
163984 | 2021-10-06 | PVC False ceiling material | Material deliverd, work under process
164011 | 2021-10-18 | Busduct material | WO issued, work under process
164125 | 2021-11-10 | Sadwitch panel with PU Foam | Today delivery
164166 | 2021-11-20 | SS Table stand | Work under process
164174 | 2021-11-22 | Butterfly valves | Deliverd
164175 | 2021-11-22 | Rubber pads | Co ordinate with supplier
164207 | 2021-11-29 | Metal doors | Cancelled by MD
164210 | 2021-11-29 | Microwave | Co ordinate with supplier, Bell electronics
164212 | 2021-11-29 | Panel boards | Co ordinatw with supplier
164225 | 2021-12-01 | Door closer | Deliverd
164232 | 2021-12-02 | Road cleaning machine | Co ordinate with supplier
164238 | 2021-12-03 | Solid bricks | Deliverd
164241 | 2021-12-04 | Copper flat, double compression glands | Deliverd
164254 | 2021-12-08 | GI U clamps | Co ordinate with supplier
164260 | 2021-12-08 | Goods lift | Co ordinate with supplier
162461 | 2021-12-08 | Bain marie, spoons, cups, tissue, paper etc | PO issuded and online purchase will be deliverd by next week
164268 | 2021-12-08 | MS Base plates, anchor bolts tandoor stones | Co ordinate with supplier
164267 | 2021-12-08 | Tandoor stone | Co ordinate with supplier
164272 | 2021-12-07 | ISMB C section | Co ordinate with supplier
164273 | 2021-12-09 | Drums, Rust remover | Co ordinate with supplier, pick up from ssllp