## KNM
Prepared by: | Kavitha
Report Date | 23-12-2021
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94991 | 15-12-2021 | Flood lights | Po issued-po no-83769
94989 | 15-12-2021 | Wall cutting wheels | Po issued-po no-83707
94988 | 15-12-2021 | Tan brown granite | Po issued-po no-83750
94987 | 15-12-2021 | Foldable opening MS Gate | Under fabrication
94985 | 2021-11-12 | Cement | Collect material from near by site
List of requisitions Where PO/WO is prepared and items have not received at site
94992 | 15-12-2021 | Electrical wires | Follow up with SSLLP
Follow up with suppleir
94990 | 15-12-2021 | Biometric device charger | Online purchase
94986 | 14-12-2021 | vedelia, Altronethra | Follow up with suppleir
94982 | 2021-12-09 | Nuvan liquid | Partly delivered, remaining to be collect from SSLLP
94980 | 2021-12-01 | panel doors | Pick up from supplier
94975 | 2021-01-12 | FRP Pipes | Follow up with suppleir
94967 | 25-11-2021 | Roff NSA, RBR Agent | Partly delivered, remaining to be collect from SSLLP
94963 | 22-11-2021 | Wifi router | Online purchase
94951 | 2021-12-11 | Tan brown granite | Partly delivered, remaining to be collect from SSLLP
94950 | 2021-12-11 | Laptop bags | Follow up with suppleir
94946 | 2021-05-12 | Gardening material | Pick up from supplier
94942 | 2021-03-12 | pendrive | Online purchase
94940 | 2021-02-12 | Shabad stone | pick up from SSLLP
94919 | 20-10-2021 | AL windows | Partly delivered, remaining to be collect from supplier
94916 | 20-10-2021 | False ceiling | Follow up with suppleir
94907 | 2021-12-10 | Pvc pipes, plain tee | Partly delivered, remaining to be collect from SSLLP
94904 | 2021-11-10 | Flat files | Partly delivered, remaining to be collect from Supplier
94902 | 2021-09-10 | Templates | Partly delivered, remaining to be collect from SSLLP