## KNM
Prepared by: | Kavitha
Report Date | 23-12-2021
Site | GVDC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
13422 | 13-08-2021 | Tp link router with sim card | PO issued, po no-83821
13382 | 19-10-2021 | Extended gate mesh | PO issued, po no-83636
13413 | 22-11-2021 | Biometric machine adaptor | Online purchase
13430 | 13-12-2021 | Digital tape and linedori | PO issued, po no-83692, 83752
13432 | 13-12-2021 | Tea flask | PO issued, po no-83580
List of requisitions Where PO/WO is prepared and items have not received at site
13345 | 2021-03-09 | RO Plant | work under process
13375 | 14-10-2021 | Wheel barrow with rubber wheels | follow up with supplier
13418 | 26-11-2021 | recron packets | follow up with supplier
13416 | 26-11-2021 | LED lights | follow up with supplier
13406 | 2021-12-11 | CPVC Material | follow up with supplier
13424 | 2021-11-11 | RMC | follow up with supplier
13425 | 2021-11-11 | Curing pipes | Pick up from SSLLP
13426 | 13-11-2021 | MS Welded mesh | follow up with supplier
13431 | 13-11-2021 | White helmets | Pick up from SSLLP
13432 | 13-12-2021 | dustbin and tissue papers | Pick up from Supplier
13435 | 13-11-2021 | Insulation tapes | Pick up from SSLLP
13436 | 14-11-2021 | Steel | Materila delivered