## KNM
Prepared by: | Kavitha
Report Date | 23-12-2021
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100563 | 2021-12-01 | Letter box | Under nagotiation
List of requisitions Where PO/WO is prepared and items have not received at site
100562 | 29-11-2021 | Sanitary items | Pick up from SSLLP Stores
100561 | 29-11-2021 | CP Fittings | Pick up from SSLLP Stores
100558 | 26-11-2021 | CP Fittings | Partly delivered, balance to be collect from SSLLP
100546 | 2021-11-03 | CP Fittings | Partly delivered, balance to be collect from SSLLP
100537 | 20-10-2021 | Curb stone | follow up with supplier
100521 | 2021-08-10 | LED Ceiling lights | Partly delivered, balance to be collect from SSLLP