## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Heights
Site: |  | 2021-12-23
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
181787 | 2021-12-16 | Cocrete tape | Local purchase by raghu
181789 | 2021-12-18 | Canvas flat pipe | PO 83927
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181775 | 2021-12-08 | Plumbing material | Deliverd
181777 | 2021-12-10 | Helmets | Deliverd
181778 | 2021-12-10 | Umbrellas | Deliverd
181784 | 2021-12-15 | Curb stones | Deliverd
181791 | 2021-12-20 | Spaces | Part deliverd balance to be deliverd