## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-12-27
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177937 | 20.08.2021 | Swimming pool Equipment's Supply | PO Issued in word format you can close this req
178191 | 23.11.2021 | Glass partition | PO 82987
178209 | 30.11.2021 | SS railing | PO 83914
178210 | 30.11.2021 | SS railing | PO 83916
178211 | 30.11.2021 | SS railing | PO 83917
178238 | 10.12.2021 | Wedge anchor bolts | PO 83665
178246 | 14.12.2021 | Wooden screws,PVC plug | PO 83685
178252 | 18.12.2021 | IN wall concealed tank,CPVC elbow | Po to be issued
178253 | 20.12.2021 | Starter | PO 83989
178255 | 20.12.2021 | Cartridge | Po to be issued
178256 | 20.12.2021 | Laptop bags | Online purchase
178259 | 22.12.2021 | Wipro garnet batten | PO 83952, 83954
178261 | 22.12.2021 | Wipro garnet batten | Po to be issued
178262 | 22.12.2021 | Armoured cable | PO 83969
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered this week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered this week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered this week.
177559 | 06.04.2021 | Ultra sprinkler HL,Malaysian brown HL | Part material delivered, remaining material to be arranged by supplier.
177562 | 06.04.2021 | 2X2 Vetrified tiles | Part material received, remaining material to be arranged by supplier
177901 | 07.08.2021 | Urban wood natural | Part material received. Remaining material no stock at Supplier
178112 | 20.10.2021 | Garbage Bin | Part material delivered Supplier has to arrange the material
178122 | 26.10.2021 | UPVC Windows | Part material received remaining material to be arranged by supplier
178125 | 29.10.2021 | Wall mixtures | Bulk order, Supplier has the material, delivery by Tuesday
178126 | 29.10.2021 | Wall mixtures | Bulk order, Supplier has the material, delivery by Tuesday
178127 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by Tuesday
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by Tuesday
178138 | 03.11.2021 | Flush doors | Today delivery
178143 | 05.11.2021 | LED lights | Deliverd
178144 | 06.11.2021 | MS box pipe | Deliverd
178152 | 08.11.2021 | Urban wood natural & Crema marfil | Pick up from SSLLP-GMR
178164 | 13.11.2021 | Janata paste | Pick up from SSLLP.
178165 | 13.11.2021 | Panel Doors ,towerbolt ,dead locks | Today delivery
178172 | 17.11.2021 | MS Square pipe | Supplier will arrange the Material Delivery by Next week
178183 | 19.11.2021 | CP wall Mixers | Pick up from SSLLP
178184 | 19.11.2021 | Sanitary material | Pick up from SSLLP
178185 | 19.11.2021 | Macherla stones | Deliverd
178198 | 26.11.2021 | SS Name plate | Work under process
178199 | 26.11.2021 | SS Name plate | Work under process
178201 | 27.11.2021 | Aluminium ladder sliding | Co ordinatewith supplier for delivery
178207 | 30.11.2021 | GI flat patti | Deliverd
178208 | 30.11.2021 | UPVC Windows | Work under process
178217 | 06.12.2021 | Roff chemical | Deliverd
178227 | 07.12.2021 | UPVC Windows | Work under process
178229 | 08.12.2021 | Flush plates | Deliverd
178230 | 08.12.2021 | Wall hung rag bolts | Deliverd
178231 | 08.12.2021 | SS name plates | Work under process
178232 | 08.12.2021 | SS name plates | Work under process
178233 | 08.12.2021 | TV Wire | Deliverd
178237 | 10.12.2021 | L brackets,MS plates | Co ordinatewith supplier for delivery
178240 | 10.12.2021 | Flat patti | Co ordinatewith supplier for delivery
178247 | 14.12.2021 | GI Non return valve,CPVC tank adaptor | Deliverd
178249 | 15.12.2021 | SS Screws 5mm | Deliverd
178251 | 18.12.2021 | Anchor bolts | Co ordinatewith supplier for delivery
178254 | 20.12.2021 | PVC Pipe,PVC 45 bend | Deliverd
178257 | 21.12.2021 | Regal biege | Deliverd
178258 | 21.12.2021 | MS Sq rod | Deliverd
178260 | 22.12.2021 | Anchor set | Deliverd