## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estaes
Site: |  | 2021-12-18
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
175431 | 2021-11-15 | Cannon camera | PO 83833
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175325 | 2021-07-20 | Solar module | Work under process
175439 | 2021-11-22 | CP Fittings | Pick up from SSLLP
175449 | 2021-12-06 | Gate lights | Deliverd
175451 | 2021-12-08 | Altek lappum | Cancelled by Site
175452 | 2021-12-11 | Panel doors, cylenderacal locks, SS Hinges | Deliverd
175453 | 2021-12-15 | Electrical wires | Pick up from SSLLP
175454 | 2021-12-16 | Indian toilet flush tank | Deliverd