## GST as on Sep 2021
Company : SILVER OAK VILLAS-III
Project : SILVER OAK VILLAS LLP - Phase III
Details of GST Bills for Villa No 101-213 as on Sep '2021
S No | Villa No | Owned By | Sales Consideration | AOC - 40% on Sale Amount | On completion | Net | Each inst | Plinth Date | Amount | RCC Date | Amount | Brick & Plstering Date | Amount | Flooring Date | Amount | On Completion Date | Amount | Total Bills as per Mile stone up to Sep'21 | Total bills raised as on Aug'21 | Bills to be raised in Sep'21 | CGST | SGST
1 | 101 | Mr. Deepak U. Mehta | 8420000 | 3368000 | 200000 | 3168000 | 792000 | 2021-01-31 | 792000 | 2021-04-01 | 792000 | [6 empty] | 1584000 | 1584000 | 0 | 0 | 0
2 | 102 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-04-01 | 780000 | [6 empty] | 1560000 | 1560000 | 0 | 0 | 0
3 | 103 | Mr. Deepak U. Mehta | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-07-30 | 780000 | [6 empty] | 1560000 | 1560000 | 0 | 0 | 0
4 | 104 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-05-05 | 780000 | [6 empty] | 1560000 | 1560000 | 0 | 0 | 0
5 | 105 | Mr. Deepak U. Mehta | 7100000 | 2840000 | 200000 | 2640000 | 660000 | 2021-01-31 | 810000 | 2021-07-16 | 810000 | [6 empty] | 1620000 | 1620000 | 0 | 0 | 0
6 | 106 | Modi Housing Pvt Ltd. | 8400000 | 3360000 | 200000 | 3160000 | 790000 | 2021-03-31 | 790000 | [8 empty] | 790000 | 790000 | 0 | 0 | 0
7 | 107 | Mrs. Harsha D. Mehta | 7800000 | 3120000 | 200000 | 2920000 | 730000 | 2021-03-31 | 730000 | [8 empty] | 730000 | 730000 | 0 | 0 | 0
8 | 108 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000 | 2021-04-23 | 860000 | [8 empty] | 860000 | 860000 | 0 | 0 | 0
9 | 109 | Mrs. Harsha D. Mehta | 8500000 | 3400000 | 200000 | 3200000 | 800000 | 2021-04-02 | 800000 | [8 empty] | 800000 | 800000 | 0 | 0 | 0
10 | 110 | Modi Housing Pvt Ltd. | 8200000 | 3280000 | 200000 | 3080000 | 770000 | 2021-03-31 | 770000 | [8 empty] | 770000 | 770000 | 0 | 0 | 0
11 | 111 | Mrs. Harsha D. Mehta | 8800000 | 3520000 | 200000 | 3320000 | 830000 | 2021-01-31 | 830000 | [8 empty] | 830000 | 830000 | 0 | 0 | 0
12 | 112 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | [8 empty] | 780000 | 780000 | 0 | 0 | 0
13 | 113 | Mr. Tejas D. Mehta | 9100000 | 3640000 | 200000 | 3440000 | 860000
14 | 114 | Modi Housing Pvt Ltd. | 8500000 | 3400000 | 200000 | 3200000 | 800000 | 2021-01-31 | 800000 | 2021-09-15 | 800000 | [6 empty] | 1600000 | 800000 | 800000 | 72000 | 72000
15 | 115 | Mr. Sudhir U. Mehta | 9110000 | 3644000 | 200000 | 3444000 | 861000 | 2021-01-31 | 861000 | 2021-08-03 | 861000 | [6 empty] | 1722000 | 861000 | 861000 | 77490 | 77490
16 | 116 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-07-19 | 780000 | [6 empty] | 1560000 | 1560000 | 0 | 0 | 0
17 | 117 | Mr. Hardik D. Mehta | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | [8 empty] | 780000 | 780000 | 0 | 0 | 0
18 | 118 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | [8 empty] | 780000 | 780000 | 0 | 0 | 0
19 | 119 | Mrs. Ruchi H. Mehta | 10000000 | 4000000 | 200000 | 3800000 | 950000 | [10 empty] | 0 | 0 | 0 | 0 | 0
20 | 120 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-04-24 | 780000 | [8 empty] | 780000 | 780000 | 0 | 0 | 0
21 | 121 | Mr. Sudhir U. Mehta | 9100000 | 3640000 | 200000 | 3440000 | 860000 | 2021-04-06 | 860000 | [8 empty] | 860000 | 860000 | 0 | 0 | 0
22 | 122 | Modi Housing Pvt Ltd. | 8200000 | 3280000 | 200000 | 3080000 | 770000 | 2021-01-31 | 770000 | 2021-08-18 | 770000 | [6 empty] | 1540000 | 1540000 | 0 | 0 | 0
23 | 123 | Mr. Sudhir U. Mehta | 8111000 | 3244400 | 200000 | 3044400 | 761100 | 2021-01-31 | 761100 | 2021-08-18 | 761100 | . | [5 empty] | 1522200 | 761100 | 761100 | 68499 | 68499
24 | 124 | Modi Housing Pvt Ltd. | 8500000 | 3400000 | 200000 | 3200000 | 800000 | 2021-01-31 | 800000 | 2021-08-18 | 800000 | [6 empty] | 1600000 | 1600000 | 0 | 0 | 0
25 | 125 | Mrs. Tejal T. Mehta | 8850000 | 3540000 | 200000 | 3340000 | 835000 | 2021-01-31 | 835000 | 2021-06-25 | 835000 | 2021-07-07 | 835000 |  |  |  |  | 2505000 | 2505000 | 0 | 0 | 0
26 | 126 | Modi Housing Pvt Ltd. | 8200000 | 3280000 | 200000 | 3080000 | 770000 | 2021-01-31 | 770000 | 2021-01-31 | 770000 | [6 empty] | 1540000 | 1540000 | 0 | 0 | 0
27 | 127 | Mrs. Aaradhana S. Mehta | 8200000 | 3280000 | 200000 | 3080000 | 770000 | 2021-01-31 | 770000 | 2021-01-31 | 770000 | 2021-08-20 | 770000 |  |  |  |  | 2310000 | 2310000 | 0 | 0 | 0
28 | 128 | Modi Housing Pvt Ltd. | 9810000 | 3924000 | 200000 | 3724000 | 931000 | 2021-05-31 | 931000 | 2021-05-31 | 931000 | [6 empty] | 1862000 | 1862000 | 0 | 0 | 0
29 | 129 | Modi Housing Pvt Ltd. | 10120000 | 4048000 | 200000 | 3848000 | 962000 | 2021-05-31 | 962000 | [8 empty] | 962000 | 962000 | 0 | 0 | 0
30 | 130 | Mrs. Aaradhana S. Mehta | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-01-31 | 780000 | 2021-03-31 | 780000 |  |  |  |  | 2340000 | 2340000 | 0 | 0 | 0
31 | 131 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-01-31 | 780000 | 2021-03-31 | 780000 |  |  |  |  | 2340000 | 2340000 | 0 | 0 | 0
32 | 132 | Mrs. Aaradhana S. Mehta | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-08-18 | 780000 | [6 empty] | 1560000 | 780000 | 780000 | 70200 | 70200
33 | 133 | Modi Housing Pvt Ltd. | 8300000 | 3320000 | 200000 | 3120000 | 780000 | 2021-01-31 | 780000 | 2021-08-18 | 780000 | [6 empty] | 1560000 | 1560000 | 0 | 0 | 0
34 | 134 | Mr. Karna S. Mehta | 8700000 | 3480000 | 200000 | 3280000 | 820000 | 2021-02-01 | 820000 | 2021-08-18 | 820000 | [6 empty] | 1640000 | 820000 | 820000 | 73800 | 73800
35 | 135 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000 | 2021-02-01 | 860000 | 2021-08-18 | 860000 | [6 empty] | 1720000 | 1720000 | 0 | 0 | 0
36 | 136 | Mr. Karna S. Mehta | 0
37 | 137 | Modi Housing Pvt Ltd. | 9000000 | 3600000 | 200000 | 3400000 | 850000 | 2021-07-17 | 850000 | [8 empty] | 850000 | 850000 | 0 | 0 | 0
38 | 138 | Smt. Rajashri K Mehta | 9000000 | 3600000 | 200000 | 3400000 | 850000 | 2021-06-02 | 850000 | [8 empty] | 850000 | 850000 | 0 | 0 | 0
39 | 139 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000 | 2021-03-31 | 860000 | [8 empty] | 860000 | 860000 | 0 | 0 | 0
40 | 140 | Smt. Rajashri K Mehta | 0
41 | 141 | Modi Housing Pvt Ltd. | 9150000 | 3660000 | 200000 | 3460000 | 865000 | 2021-06-22 | 865000 | [8 empty] | 865000 | 865000 | 0 | 0 | 0
42 | 142 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000 | 2021-06-10 | 860000 | [8 empty] | 860000 | 860000 | 0 | 0 | 0
43 | 143 | Modi Housing Pvt Ltd. | 9000000 | 3600000 | 200000 | 3400000 | 850000 | 2021-04-14 | 850000 | [8 empty] | 850000 | 850000 | 0 | 0 | 0
44 | 144 | Modi Housing Pvt Ltd. | 9070000 | 3628000 | 200000 | 3428000 | 857000 | 2021-04-19 | 857000 | 2021-09-16 | 857000 | [6 empty] | 1714000 | 857000 | 857000 | 77130 | 77130
45 | 145 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000 | 2021-07-05 | 860000 | [8 empty] | 860000 | 860000 | 0 | 0 | 0
46 | 146 | Modi Housing Pvt Ltd. | 0
47 | 147 | Modi Housing Pvt Ltd. | 0
48 | 148 | Modi Housing Pvt Ltd. | 8930000 | 3572000 | 200000 | 3372000 | 843000
49 | 149 | Modi Housing Pvt Ltd. | 8600000 | 3440000 | 200000 | 3240000 | 810000
50 | 150 | Modi Housing Pvt Ltd. | 8600000 | 3440000 | 200000 | 3240000 | 810000
51 | 151 | Modi Housing Pvt Ltd. | 8600000 | 3440000 | 200000 | 3240000 | 810000
52 | 152 | Modi Housing Pvt Ltd. | 9381000 | 3752400 | 200000 | 3552400 | 888100
53 | 153 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000
54 | 154 | Modi Housing Pvt Ltd. | 9100000 | 3640000 | 200000 | 3440000 | 860000
55 | 155 | Modi Housing Pvt Ltd. | 8850000 | 3540000 | 200000 | 3340000 | 835000
56 | 156 | Modi Housing Pvt Ltd. | 7350000 | 2940000 | 200000 | 2740000 | 685000 | 2021-09-13 | 685000 | [8 empty] | 685000 | 0 | 685000 | 61650 | 61650
57 | 157 | Modi Housing Pvt Ltd. | 8850000 | 3540000 | 200000 | 3340000 | 835000 | 2021-09-18 | 835000 | [8 empty] | 835000 | 0 | 835000 | 75150 | 75150
58 | 158 | Modi Housing Pvt Ltd. | 9800000 | 3920000 | 200000 | 3720000 | 930000
59 | 159 | Modi Housing Pvt Ltd. | 8600000 | 3440000 | 200000 | 3240000 | 810000
60 | 160 | Modi Housing Pvt Ltd. | 9725000 | 3890000 | 200000 | 3690000 | 922500
61 | 161 | Modi Housing Pvt Ltd. | 0
62 | 162 | Modi Housing Pvt Ltd. | 7850000 | 3140000 | 200000 | 2940000 | 735000
63 | 163 | Modi Housing Pvt Ltd. | 9700000 | 3880000 | 200000 | 3680000 | 920000 | 2021-06-30 | 920000 | [8 empty] | 920000 | 920000 | 0 | 0 | 0
64 | 164 | Modi Housing Pvt Ltd. | 0
65 | 165 | Modi Housing Pvt Ltd. | 5000000 | 2000000 | 200000 | 1800000 | 450000 | 2021-07-17 | 450000 | [8 empty] | 450000 | 450000 | 0 | 0 | 0
66 | 166 | Modi Housing Pvt Ltd. | 0
67 | 167 | Modi Housing Pvt Ltd. | 0
68 | 168 | Modi Housing Pvt Ltd. | 0
69 | 169 | Modi Housing Pvt Ltd. | 0
70 | 170 | Modi Housing Pvt Ltd. | 0
71 | 171 | Modi Housing Pvt Ltd. | 0
72 | 172 | Modi Housing Pvt Ltd. | 0
73 | 173 | Modi Housing Pvt Ltd. | 0
74 | 174 | Modi Housing Pvt Ltd. | 10000000 | 4000000 | 200000 | 3800000 | 950000
75 | 175 | Modi Housing Pvt Ltd. | 0
76 | 176 | Modi Housing Pvt Ltd. | 0
77 | 177 | Modi Housing Pvt Ltd. | 0
78 | 178 | Modi Housing Pvt Ltd. | 0
79 | 179 | Modi Housing Pvt Ltd. | 9800000 | 3920000 | 200000 | 3720000 | 930000
80 | 180 | Modi Housing Pvt Ltd. | 6948000 | 2779200 | 200000 | 2579200 | 644800 | 2021-07-08 | 644800 | [8 empty] | 644800 | 644800 | 0 | 0 | 0
81 | 181 | Modi Housing Pvt Ltd. | 9600000 | 3840000 | 200000 | 3640000 | 910000 | 2021-07-03 | 910000 | [8 empty] | 910000 | 910000 | 0 | 0 | 0
82 | 182 | Modi Housing Pvt Ltd. | 9950000 | 3980000 | 200000 | 3780000 | 945000 | 2021-06-30 | 945000 | [8 empty] | 945000 | 945000 | 0 | 0 | 0
83 | 183 | Modi Housing Pvt Ltd. | 10000000 | 4000000 | 200000 | 3800000 | 950000 | 2021-06-26 | 950000 | [8 empty] | 950000 | 950000 | 0 | 0 | 0
84 | 184 | Modi Housing Pvt Ltd. | 0
85 | 185 | Modi Housing Pvt Ltd. | 10000000 | 4000000 | 200000 | 3800000 | 950000 | 2021-09-15 | 950000 | [8 empty] | 950000 | 0 | 950000 | 85500 | 85500
86 | 186 | Modi Housing Pvt Ltd. | 0
87 | 187 | Modi Housing Pvt Ltd. | 0
88 | 188 | Modi Housing Pvt Ltd. | 0
89 | 189 | Modi Housing Pvt Ltd. | 0
90 | 190 | Modi Housing Pvt Ltd. | 0
91 | 191 | Modi Housing Pvt Ltd. | 0
92 | 192 | Modi Housing Pvt Ltd. | 0
93 | 193 | Modi Housing Pvt Ltd. | 0
94 | 194 | Modi Housing Pvt Ltd. | 0
95 | 195 | Modi Housing Pvt Ltd. | 0
96 | 196 | Modi Housing Pvt Ltd. | 0
97 | 197 | Modi Housing Pvt Ltd. | 0
98 | 198 | Modi Housing Pvt Ltd. | 0
99 | 199 | Modi Housing Pvt Ltd. | 0
100 | 200 | Modi Housing Pvt Ltd. | 0
101 | 201 | Modi Housing Pvt Ltd. | 0
102 | 202 | Modi Housing Pvt Ltd. | 0
103 | 203 | Modi Housing Pvt Ltd. | 0
104 | 204 | Modi Housing Pvt Ltd. | 0
105 | 205 | Modi Housing Pvt Ltd. | 0
106 | 206 | Modi Housing Pvt Ltd. | 0
107 | 207 | Modi Housing Pvt Ltd. | 0
108 | 208 | Modi Housing Pvt Ltd. | 0
109 | 209 | Modi Housing Pvt Ltd. | 0
110 | 210 | Modi Housing Pvt Ltd. | 0
111 | 211 | Modi Housing Pvt Ltd. | 0
112 | 212 | Modi Housing Pvt Ltd. | 0
113 | 213 | Modi Housing Pvt Ltd. | 0
114 | 214 | Modi Housing Pvt Ltd. | 0
|  |  | 153991000 | 61596400 | 3600000 | 57996400 | 14499100 |  | 12839100 | 443602 | 7989100 | 133098 | 2385000 | 0 | 0 | 0 | 0 | 23213200 | 19991100 | 3222100 | 289989 | 289989

## Exempt sales Sep 2021
Company : MODI HOUSING PVT LTD-SOV III
Project : SILVER OAK VILLAS LLP - Phase III
Details of Exempt Bills for Villa No 101-213 as on Sep-2021
[18 empty] | upto current month | upto Mar'2020 | up to previous month |  | only current month invoices
S No | Villa No | Owned By | Sales Consideration | AOS -60% on Sale Amount | On completion | Net | Each inst | Plinth Date | Amount | RCC Date | Amount | Brick & Plstering Date | Amount | Flooring Date | Amount | On Completion Date | Amount | Total Bills as per Mile stone up to Sep'21 | Total Exempt Bills Raised as on March'20 | Total Exempt bills raised as on Aug'2021 | Total Sales upto prevoius month | Bills to raised in Sep'21 (current month sales) | Credit Notes | Bills to raised in Mar'21
1 | 101 | Mr. Deepak U. Mehta | 8420000 | 5052000 | 200000 | 4852000 | 1213000 | 2021-01-31 | 1213000 | 2021-04-01 | 1213000 | [6 empty] | 2426000 | 0 | 0 | 0 | 2426000
2 | 102 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-04-01 | 1195000 | [6 empty] | 2390000 | 1225000 | 1165000 | 2390000 | 0 | 3285000 | 3285000
3 | 103 | Mr. Deepak U. Mehta | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | [8 empty] | 1195000 |  | 0 | 0 | 1195000
4 | 104 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-05-05 | 1195000 | [6 empty] | 2390000 | 1225000 | -30000 | 2390000 | 0 | 3285000 | 3285000
5 | 105 | Mr. Deepak U. Mehta | 7100000 | 4260000 | 200000 | 4060000 | 1015000 | 2021-01-31 | 1015000 | [8 empty] | 1015000 |  | 0 | 0 | 1015000
6 | 106 | Modi Housing Pvt Ltd. | 8400000 | 5040000 | 200000 | 4840000 | 1210000 | 2021-03-31 | 1210000 | [8 empty] | 1210000 |  | 1210000 | 1210000 | 0 | 0 | 0
7 | 107 | Mrs. Harsha D. Mehta | 7800000 | 4680000 | 200000 | 4480000 | 1120000 | 2021-03-31 | 1120000 | [8 empty] | 1120000 |  |  | 0 | 1120000
8 | 108 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | 2021-04-23 | 1315000 | [8 empty] | 1315000 |  | 1315000 | 1315000 | 0 | 225000 | 225000
9 | 109 | Mrs. Harsha D. Mehta | 8500000 | 5100000 | 200000 | 4900000 | 1225000 | 2021-04-02 | 1225000 | [8 empty] | 1225000 |  | 225000 | 225000 | 1000000
10 | 110 | Modi Housing Pvt Ltd. | 8200000 | 4920000 | 200000 | 4720000 | 1180000 | 2021-03-31 | 1180000 | [8 empty] | 1180000 | 1225000 | -45000 | 1180000 | 0 | 0 | 0
11 | 111 | Mrs. Harsha D. Mehta | 8800000 | 5280000 | 200000 | 5080000 | 1270000 | 2021-01-31 | 1270000 | [8 empty] | 1270000 |  | 0 | 0 | 1270000
12 | 112 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | [8 empty] | 1195000 |  | 1195000 | 1195000 | 0 | 990000 | 990000
13 | 113 | Mr. Tejas D. Mehta | 9100000
14 | 114 | Modi Housing Pvt Ltd. | 8500000 | 5100000 | 200000 | 4900000 | 1225000 | 2021-01-31 | 1225000 | 2021-09-15 | 1225000 | [6 empty] | 2450000 |  | 1225000 | 1225000 | 1225000 | 0 | 1225000
15 | 115 | Mr. Sudhir U. Mehta | 9110000 | 5466000 | 200000 | 5266000 | 1316500 | 2021-01-31 | 1316500 | 2021-08-03 | 1316500 | [6 empty] | 2633000 |  | 0 | 0 | 2633000
16 | 116 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-07-19 | 1195000 | [6 empty] | 2390000 | 1225000 | 1165000 | 2390000 | 0 | 3285000 | 3285000
17 | 117 | Mr. Hardik D. Mehta | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | [8 empty] | 1195000 |  | 0 | 0 | 1195000
18 | 118 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | [8 empty] | 1195000 | 225000 | 970000 | 1195000 | 0 | 30000 | 30000
19 | 119 | Mrs. Ruchi H. Mehta | 10000000 | 6000000 | 200000 | 5800000 | 1450000 | 2021-04-01 | 1450000 | [8 empty] | 1450000 |  |  | 0 | 1450000
20 | 120 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-04-24 | 1195000 | [8 empty] | 1195000 |  | 1195000 | 1195000 | 0 | 1225000 | 1225000
21 | 121 | Mr. Sudhir U. Mehta | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | 2021-04-06 | 1315000 | [8 empty] | 1315000 |  | 0 | 0 | 1315000
22 | 122 | Modi Housing Pvt Ltd. | 8200000 | 4920000 | 200000 | 4720000 | 1180000 | 2021-01-31 | 1180000 | 2021-08-18 | 1180000 | [6 empty] | 2360000 | 1225000 | -45000 | 1180000 | 1135000 | 45000 | 1180000
23 | 123 | Mr. Sudhir U. Mehta | 8111000 | 4866600 | 200000 | 4666600 | 1166650 | 2021-01-31 | 1166650 | 2021-08-18 | 1166650 | [6 empty] | 2333300 |  | 0 | 0 | 2333300
24 | 124 | Modi Housing Pvt Ltd. | 8500000 | 5100000 | 200000 | 4900000 | 1225000 | 2021-01-31 | 1225000 | 2021-08-18 | 1225000 | [6 empty] | 2450000 |  | 2450000 | 2450000 | 0 | 500000 | 500000
25 | 125 | Mrs. Tejal T. Mehta | 8850000 | 5310000 | 200000 | 5110000 | 1277500 | 2021-01-31 | 1277500 | 2021-06-25 | 1277500 | [6 empty] | 2555000 |  | 0 | 0 | 2555000
26 | 126 | Modi Housing Pvt Ltd. | 8200000 | 4920000 | 200000 | 4720000 | 1180000 | 2021-01-31 | 1180000 | 2021-01-31 | 1180000 | 2021-07-07 | 1180000 |  |  |  |  | 3540000 | 225000 | 5375000 | 3540000 | 0 | 2060000 | 2060000
27 | 127 | Mrs. Aaradhana S. Mehta | 8200000 | 4920000 | 200000 | 4720000 | 1180000 | 2021-01-31 | 1180000 | 2021-01-31 | 1180000 | 2021-08-20 | 1180000 |  |  |  |  | 3540000 |  | 0 | 0 | 3540000
28 | 128 | Modi Housing Pvt Ltd. | 9810000 | 5886000 | 200000 | 5686000 | 1421500 | 2021-05-31 | 1421500 | 2021-05-31 | 1421500 | [6 empty] | 2843000 | 0 | 0 | 2843000 | 0
29 | 129 | Modi Housing Pvt Ltd. | 10120000 | 6072000 | 200000 | 5872000 | 1468000 | 2021-05-31 | 1468000 | [8 empty] | 1468000 |  |  | 1468000 | 0
30 | 130 | Mrs. Aaradhana S. Mehta | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-01-31 | 1195000 | 2021-03-31 | 1195000 |  |  |  |  | 3585000 |  | 0 | 0 | 3585000
31 | 131 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-01-31 | 1195000 | 2021-03-31 | 1195000 |  |  |  |  | 3585000 | 0 | 1495000 | 3585000 | 0 | 0 | 0
32 | 132 | Mrs. Aaradhana S. Mehta | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-08-18 | 1195000 | [6 empty] | 2390000 |  | 1195000 | 1195000 | 1195000
33 | 133 | Modi Housing Pvt Ltd. | 8300000 | 4980000 | 200000 | 4780000 | 1195000 | 2021-01-31 | 1195000 | 2021-08-18 | 1195000 | [6 empty] | 2390000 | 1225000 | -30000 | 1165000 | 1195000 | 30000 | 1225000
34 | 134 | Mr. Karna S. Mehta | 8700000 | 5220000 | 200000 | 5020000 | 1255000 |  |  | 2021-08-18 | 1255000 | [6 empty] | 1255000 |  | 0 | 0 | 1255000
35 | 135 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | 2021-02-28 | 1315000 | 2021-08-18 | 1315000 | [6 empty] | 2630000 |  | 2630000 | 2630000 | 0 | 0 | 0
36 | 136 | Mr. Karna S. Mehta | 0
37 | 137 | Modi Housing Pvt Ltd. | 9000000 | 5400000 | 200000 | 5200000 | 1300000 | 2021-07-17 | 1300000 | [8 empty] | 1300000 | 0 | 1300000 | 1300000 | 0
38 | 138 | Smt. Rajashri K Mehta | 9000000 | 5400000 | 200000 | 5200000 | 1300000 | 2021-06-02 | 1300000
39 | 139 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | 2021-03-31 | 1315000 | [8 empty] | 1315000 | 0 | 1315000 | 1315000 | 0 | 0 | 0
40 | 140 | Smt. Rajashri K Mehta | 0
41 | 141 | Modi Housing Pvt Ltd. | 9150000 | 5490000 | 200000 | 5290000 | 1322500 | 2021-06-22 | 1322500 | [8 empty] | 1322500 | 0 | 1322500 | 1322500 | 0
42 | 142 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | 2021-06-10 | 1315000 | [8 empty] | 1315000 |  | 1315000 | 1315000 | 0 | 0 | 0
43 | 143 | Modi Housing Pvt Ltd. | 9000000 | 5400000 | 200000 | 5200000 | 1300000 | 2021-04-14 | 1300000 | [8 empty] | 1300000 |  | 1300000 | 1300000 | 0
44 | 144 | Modi Housing Pvt Ltd. | 9070000 | 5442000 | 200000 | 5242000 | 1310500 | 2021-04-19 | 1310500 | 2021-09-16 | 1310500 | [6 empty] | 2621000 |  | 1310500 | 1310500 | 1310500
45 | 145 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | 2021-07-05 | 1315000 | [8 empty] | 1315000 |  | 1315000 | 1315000 | 0
46 | 146 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
47 | 147 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
48 | 148 | Modi Housing Pvt Ltd. | 8930000 | 5358000 | 200000 | 5158000 | 1289500 | [10 empty] | 0 |  |  | 0 | 0
49 | 149 | Modi Housing Pvt Ltd. | 8600000 | 5160000 | 200000 | 4960000 | 1240000 | [10 empty] | 0 |  |  | 0 | 0
50 | 150 | Modi Housing Pvt Ltd. | 8600000 | 5160000 | 200000 | 4960000 | 1240000 | [10 empty] | 0 |  |  | 0 | 0
51 | 151 | Modi Housing Pvt Ltd. | 8600000 | 5160000 | 200000 | 4960000 | 1240000 | [10 empty] | 0 |  |  | 0 | 0
52 | 152 | Modi Housing Pvt Ltd. | 9381000 | 5628600 | 200000 | 5428600 | 1357150 | [10 empty] | 0 |  |  | 0 | 0
53 | 153 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | [10 empty] | 0 |  |  | 0 | 0
54 | 154 | Modi Housing Pvt Ltd. | 9100000 | 5460000 | 200000 | 5260000 | 1315000 | [10 empty] | 0 |  |  | 0 | 0
55 | 155 | Modi Housing Pvt Ltd. | 8850000 | 5310000 | 200000 | 5110000 | 1277500 | [10 empty] | 0 |  |  | 0 | 0
56 | 156 | Modi Housing Pvt Ltd. | 7350000 | 4410000 | 200000 | 4210000 | 1052500 | 2021-09-13 | 1052500 | [8 empty] | 1052500 |  |  | 0 | 1052500
57 | 157 | Modi Housing Pvt Ltd. | 8850000 | 5310000 | 200000 | 5110000 | 1277500 | 2021-09-18 | 1277500 | [8 empty] | 1277500 |  |  | 0 | 1277500 | 1225000 | 2502500
58 | 158 | Modi Housing Pvt Ltd. | 9800000 | 5880000 | 200000 | 5680000 | 1420000 | [10 empty] | 0 |  |  | 0 | 0
59 | 159 | Modi Housing Pvt Ltd. | 8600000 | 5160000 | 200000 | 4960000 | 1240000 | [10 empty] | 0 |  |  | 0 | 0
60 | 160 | Modi Housing Pvt Ltd. | 9725000 | 5835000 | 200000 | 5635000 | 1408750 | [10 empty] | 0 |  |  | 0 | 0
61 | 161 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
62 | 162 | Modi Housing Pvt Ltd. | 7850000 | 4710000 | 200000 | 4510000 | 1127500 | [10 empty] | 0 |  |  | 0 | 0
63 | 163 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
64 | 164 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
65 | 165 | Modi Housing Pvt Ltd. | 5000000 | 3000000 | 200000 | 2800000 | 700000 | 2021-07-17 | 700000 | [8 empty] | 700000 |  | 700000 | 700000 | 0
66 | 166 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
67 | 167 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
68 | 168 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
69 | 169 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
70 | 170 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
71 | 171 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
72 | 172 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
73 | 173 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
74 | 174 | Modi Housing Pvt Ltd. | 10000000 | 6000000 | 200000 | 5800000 | 1450000 | [10 empty] | 0 |  |  | 0 | 0
75 | 175 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
76 | 176 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
77 | 177 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
78 | 178 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
79 | 179 | Modi Housing Pvt Ltd. | 9800000 | 5880000 | 200000 | 5680000 | 1420000 | [10 empty] | 0 |  |  | 0 | 0
80 | 180 | Modi Housing Pvt Ltd. | 6948000 | 4168800 | 200000 | 3968800 | 992200 | 2021-07-08 | 992200 | [8 empty] | 992200 |  | 992200 | 992200 | 0
81 | 181 | Modi Housing Pvt Ltd. | 9600000 | 5760000 | 200000 | 5560000 | 1390000 | 2021-07-03 | 1390000 | [8 empty] | 1390000 |  | 1390000 | 1390000 | 0
82 | 182 | Modi Housing Pvt Ltd. | 9950000 | 5970000 | 200000 | 5770000 | 1442500 | 2021-06-30 | 1442500 | [8 empty] | 1442500 | 0 | 1442500 | 1442500 | 0
83 | 183 | Modi Housing Pvt Ltd. | 10000000 | 6000000 | 200000 | 5800000 | 1450000 | 2021-06-26 | 1450000 | [8 empty] | 1450000 | 0 | 1450000 | 1450000 | 0
84 | 184 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
85 | 185 | Modi Housing Pvt Ltd. | 10000000 | 6000000 | 200000 | 5800000 | 1450000 | 2021-09-15 | 1450000 | [8 empty] | 1450000 | 0 | 0 | 0 | 1450000
86 | 186 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
87 | 187 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
88 | 188 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
89 | 189 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
90 | 190 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
91 | 191 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
92 | 192 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
93 | 193 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
94 | 194 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
95 | 195 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
96 | 196 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
97 | 197 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
98 | 198 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
99 | 199 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
100 | 200 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
101 | 201 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
102 | 202 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
103 | 203 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
104 | 204 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
105 | 205 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
106 | 206 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
107 | 207 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
108 | 208 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
109 | 209 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
110 | 210 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
111 | 211 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
112 | 212 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
113 | 213 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
114 | 214 | Modi Housing Pvt Ltd. | 0 | [14 empty] | 0 |  |  | 0 | 0
|  |  | 412684000 | 247610400 | 9400000 | 238210400 | 59552600 |  | 41212200 |  | 14832000 | 88670 | 2375000 | 0 | 0 | 0 | 0 | 58419200 | 7800000 | 36392700 | 49698700 | 8645500 | 16185000 | 21017500
Formulas:
Amount = [Each inst]