## KNM
Prepared by: | Kavitha
Report Date | 2022-01-01
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95005 | 24-12-2021 | Switches | PO Issued, PO No-83944
95004 | 24-12-2021 | Electrical Wires | PO Issued, PO No-84062
95000 | 21-12-2021 | Bombay brooms | PO Issued, PO No-84224
94987 | 15-12-2021 | Foldable Opening MS Gate | PO Issued, PO No-84625
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95003 | 23-12-2021 | Vetrified tiles | pick up from SSLLP
95002 | 22-12-2021 | Altek lappam | pick up from SSLLP
95001 | 21-12-2021 | MS nails | pick up from SSLLP
94999 | 21-12-2021 | Aroldite, recron | Partly delivered, remaining to be collect from supplier
94996 | 18-12-2021 | PVC Wenge ceiling, U patti | Follow up with suppleir
94993 | 17-12-2021 | White papers | Partly delivered, remaining to be collect from supplier
94991 | 15-12-2021 | Flood lights | Follow up with suppleir
94990 | 15-12-2021 | Biometric device charger | Online purchase
94989 | 15-12-2021 | Wall cutting blades | Follow up with suppleir
94988 | 15-12-2021 | Tan brown granite | pick up from SSLLP
94986 | 14-12-2021 | Vedelia, Altronetra | Follow up with suppleir
94982 | 2021-09-12 | Nuvan liquid | Partly delivered, remaining to be collect from suppleir
94980 | 2021-09-12 | Panel doors | Follow up with suppleir
94975 | 2021-01-12 | FRP pipes | Follow up with suppleir
94951 | 2021-12-11 | Tan brown granite | Partly delivered, remaining to be collect from supplier
94950 | 2021-12-11 | Laptop bags | Online purchase
94946 | 2021-05-11 | Garnening material | Follow up with suppleir
94942 | 2021-03-11 | Pendrive | Online purchase
94940 | 2021-02-11 | Shabad stone | pick up from SSLLP
94923 | 20-10-2021 | Al windows | Follow up with suppleir
94919 | 20-10-2021 | Al windows | Partly delivered, remaining to be collect from supplier
94902 | 2021-09-10 | Templates | Partly delivered, remaining to be collect from supplier