## KNM
Prepared by: | Kavitha
Report Date | 17-01-2022
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94987 | 15-12-2021 | Foldable opening MS Gate | PO Issued, PO No-84625
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95009 | 30-12-2021 | Travertine carolina | pick up from SSLLP
95008 | 30-12-2021 | Vetrified tiles | pick up from SSLLP
95006 | 27-12-2021 | Labour helment and jakets | pick up from SSLLP
95003 | 23-12-2021 | Vetrified tiles | pick up from SSLLP
94996 | 18-12-2021 | PVC Wenge ceiling, U patti | Follow up with suppleir
94990 | 15-12-2021 | Biometric device charger | Online purchase
94989 | 15-12-2021 | Wall cutting wheels | Follow up with suppleir
94982 | 2021-09-12 | Nuvan liquid, blitex poweder, DAP, Urea | Partly delivered, remaining to be collect from supplier
94980 | 2021-09-12 | Panel doors | Partly delivered, remaining to be collect from supplier
94975 | 2021-12-01 | FRP pipes, Couplers | Follow up with suppleir
94950 | 2021-12-11 | Laptop bags | Online purchase
94946 | 2021-05-11 | Gardening material | Follow up with suppleir
94942 | 2021-03-11 | Pendrive | Online purchase
94940 | 2021-02-11 | Shabad Stone | pick up from SSLLP
94923 | 20-10-2021 | Al windows | pick up from SSLLP
94902 | 2021-09-10 | Templates | Partly delivered, remaining to be collect from SSLLP