## KNM
Prepared by: | Kavitha
Report Date | 19-01-2022
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94991 | 15-12-2021 | Flood lights | PO Issued, PO No-83769
94989 | 15-12-2021 | Wall cutting blades | PO Issued, PO No-83707
94988 | 15-12-2021 | Tan brown granite | PO Issued, PO No-83750
94987 | 15-12-2021 | Foldable opening MS gate | PO Issued, PO No-84625
94985 | 2021-11-12 | Cement | Cancelled
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
94992 | 15-12-2021 | Electrical wires | pick up from SSLLP
94990 | 15-12-2021 | Biometric device charger | Online purchase
94986 | 14-12-2021 | Vedela Altronethra | Follow up with suppleir
94982 | 2021-09-12 | Nuvan Liquid | Partly delivered, remaining to be collect from supplier
94980 | 2021-09-12 | Panel Doors | Follow up with suppleir
94975 | 2021-01-12 | FRP pipes | Follow up with suppleir
94967 | 25-11-2021 | Roff NSA, RBR bonding agent | Partly delivered, remaining to be collect from supplier
94963 | 22-11-2021 | Wifi router | Online purchase
94951 | 2021-12-11 | Tan brown granite | Partly delivered, remaining to be collect from suppleir
94950 | 2021-12-11 | Lpatop bags | Online purchase
94946 | 2021-05-11 | Gardening material | Partly delivered, remaining to be collect from supplier
94942 | 2021-03-01 | Pendrive | Online purchase
94940 | 2021-02-11 | Shabad stone | pick up from SSLLP
94919 | 20-10-2021 | AL windows | Partly delivered, remaining to be collect from supplier
94916 | 20-10-2021 | Flase ceiling | Follow up with suppleir
94907 | 2021-12-10 | PVC Pipes | Partly delivered, remaining to be collect from supplier
94904 | 2021-11-10 | Flat files | Follow up with suppleir
94902 | 2021-09-10 | Templates | Partly delivered, remaining to be collect from supplier