## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2022-01-15
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
164173 | 2021-11-22 | FRP Manholes | Samples to get from suppliers
164263 | 2021-12-08 | Organic waste converter | PO 84332
164264 | 2021-12-08 | Digital energy meter | Cancelled by Likitha
164265 | 2021-12-08 | Electromegnetic flow meter | Cancelled by Likitha
164281 | 2021-12-11 | Channel brackets, GI U clamp, nuts | PO 83600
164301 | 2021-12-15 | Calmshell cards | Online purchase
164256 | 2021-12-08 | L Patti, Ssscerws | PO 83544, 83612
162302 | 2021-12-16 | Fishers, wooden screws | PO 83777
164305 | 2021-12-17 | Alaram gong valve | Hold by Waseem
164313 | 2021-12-18 | Bathroom tiles- | Cancelled due to not mentioned the specifications
164323 | 2021-12-21 | LED Sign boards | Requisition not found, send it again
164332 | 2021-12-24 | Visiting cards | Promotions to follow up
164340 | 2021-12-27 | Screws, Hinges | PO 84094
164347 | 2021-12-27 | Pressure omicron make transmiter | PO 84120
164348 | 2021-12-27 | Vacuum degasser | PO 84231
164349 | 2021-12-27 | STP/ETP Matrial | PO 84302
164366 | 2021-12-30 | GI Pipe wrapping material | Quotes to be receivd
164369 | 2021-12-31 | CPVC Plain elbow, coupling, clamps | PO 84257
164934 | 2022-01-07 | SS Single hydrant | Requisition not found, send it again
164398 | 2022-01-10 | RMC | PO 84673
164402 | 2022-01-10 | Breathing analasys | Online purchase
164403 | 2022-01-10 | Walkie taklie | Cancelled by MD
164405 | 2022-01-10 | RMC | PO 84674
164406 | 2022-01-11 | RMC | PO 84705
164407 | 2022-01-11 | Suface boxes, syntes box | Cancelled
164410 | 2021-01-11 | Shabhad stone | PO 84599
164411 | 2022-01-11 | Mobile camera box | PO 84679
164412 | 2022-01-11 | 16 sqmm 4 core wire | PO to be issue
164413 | 2022-01-11 | Hammer drill | PO 84695, 84701
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163601 | 2021-06-30 | HT Works | Work under process
163704 | 2021-08-07 | ACP Cladding | Work under process
163889 | 2021-09-23 | Fire safety equipments | Work under process
163984 | 2021-10-06 | PVC False ceiling material | Material deliverd, work under process
164011 | 2021-10-18 | Busduct material | WO issued, work under process
164175 | 2021-11-22 | Rubber pads | Co ordinate with supplier
164207 | 2021-11-29 | Metal doors | Cancelled By md
164210 | 2021-11-29 | Microwave | Co ordinate with supplier, Bell electronics
164212 | 2021-11-29 | Panel boards | Co ordinatw with supplier
164213 | 2021-11-29 | Panel boards | Co ordinate with supplier
162461 | 2021-12-08 | Bain marie, spoons, cups, tissue, paper etc | Co ordinate with supplier
164260 | 2021-12-08 | Goods lift | Co ordinate with supplier
164280 | 2021-12-11 | BTU Meater | Supplier will arragne the material
164289 | 2021-12-13 | Solar Module | Co ordinate with supplier
164304 | 2021-12-18 | Fire safety equipments | Work under process
164311 | 2021-12-18 | False ceiling work | Work under process
164327 | 2021-12-23 | MCB | Take from shubham enterprises
164345 | 2021-12-27 | White primer | Pick up from Supplier
164371 | 2021-12-31 | Chiller material | Part material deliverd
164385 | 2022-01-05 | Base plates, ms pipes, elbows | Part material deliverd
164390 | 2022-01-07 | Armourd cable, MCCB,PVC Pipes, isolaters | Pick up from SSLLP
164401 | 2021-01-11 | Pump starter | Pick up from supplier