## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2022-01-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
178246 | 14.12.2021 | Wooden screws,PVC plug | PO 83685
178270 | 24.12.2021 | EPDM Flooring | Quotes to be received
178301 | 06.01.2022 | Jerry cans | Online purchase
178303 | 07.01.2022 | Glass single doors | PO 84508
178310 | 11.01.2022 | Playground area equipment | Quotes to be received
178312 | 11.01.2022 | Glass partition | PO 84509
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | 84476 PO
178317 | 12.01.2022 | Sliding windows | PO 84540, 84542
178318 | 12.01.2022 | Mobile camera box | PO 84620
178319 | 12.01.2022 | Self inking stamp | PO to be issued
178320 | 14.01.2022 | Birla putty | PO to be issued
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Part material deliverd
177488 | 18.03.2021 | MCBs,modular plate ,socket | Part material deliverd
177498 | 19.03.2021 | Stainless steel sink | Part material deliverd
177559 | 06.04.2021 | Ultra sprinkler HL,Malaysian brown HL | Part material deliverd
177562 | 06.04.2021 | 2X2 Vetrified tiles | Part material deliverd
177901 | 07.08.2021 | Urban wood natural | Part material deliverd
178112 | 20.10.2021 | Garbage Bin | Supplier not responding
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Part material deliverd
178126 | 29.10.2021 | Wall mixtures | Part material deliverd
178127 | 29.10.2021 | Wall hung WC | Part material deliverd
178128 | 29.10.2021 | Wall hung WC | Part material deliverd
178143 | 05.11.2021 | LED lights | Part material deliverd
178144 | 06.11.2021 | MS box pipe | Part material deliverd
178147 | 06.11.2021 | Kitchen unit | Work under progress
178152 | 08.11.2021 | Urban wood natural & Crema marfil | Part material deliverd
178164 | 13.11.2021 | Janata paste | Pick up from SSLLP
178172 | 17.11.2021 | MS Square pipe | Supplier will arrange the Material Delivery by this week
178184 | 19.11.2021 | Sanitary material | Part material deliverd, balance to be receive
178198 | 26.11.2021 | SS Name plate | Work under progress
178199 | 26.11.2021 | SS Name plate | Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178217 | 06.12.2021 | Roff chemical | Part material received remaining material to be arranged by supplier
178227 | 07.12.2021 | UPVC Windows | Work under progress
178230 | 08.12.2021 | Wall hung rag bolts | Part material received remaining material no stock at supplier
178231 | 08.12.2021 | SS name plates | Work under progress
178232 | 08.12.2021 | SS name plates | Work under progress
178237 | 10.12.2021 | L brackets,MS plates | Part material received, remaining Supplier has to arrange the material
178240 | 10.12.2021 | Flat patti | Part material received, remaining Supplier has to arrange the material
178268 | 24.12.2021 | Timer,DB Board single phase | Part material received remaining material delivery in this week
178276 | 27.12.2021 | Cement pots | Part material received remaining material delivery in this week
178284 | 28.12.2021 | Fishers | Material delivery on Monday
178293 | 04.01.2022 | Flush tank | Part material deliverd balance to be receive
178295 | 05.01.2022 | Light above main door | Material delivery on Monday
178298 | 06.01.2022 | SS screws and fishers | Material delivery in this week
178300 | 06.01.2022 | 3 pole conductor | Material delivery in this week
178305 | 08.01.2022 | Paper bundles | Pick up from SSLLP
178309 | 10.01.2022 | 4 Pole isolator | Material delivery in this week