## KNM
Prepared by: | Kavitha
Report Date | 2022-10-02
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95032 | 17-01-2021 | UPVC Windows | Po issued, Po no- 85197
95033 | 17-01-2021 | upvc Sliding doors | Po issued, Po no- 85198
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95006 | 27-12-2021 | Labour helmets | Partly delivered, remaining to be collect from ssllp
95023 | 2022-11-01 | Canon cemera | pick up from SSLLP
95024 | 2022-12-01 | Lights | Partly delivered, remaining to be collect from supplier
95036 | 18-01-2021 | Safety shoes | pick up from SSLLP
95039 | 21-01-2021 | Laptop bags | Partly delivered, remaining to be collect from SSLLP
95040 | 24-01-2022 | Door frames | Partly delivered, remaining to be collect from supplier
95045 | 24-01-2022 | Lights | Partly delivered, remaining to be collect from supplier
95041 | 24-01-2022 | Welspun flooring carpet tiles | pick up from SSLLP
95052 | 29-01-2022 | Shower head | Partly delivered, remaining to be collect from ssllp