## SOV III
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-02-05
Site |  | MPPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178301 | 06.01.2022 | Jerry cans | Online purchase
178310 | 11.01.2022 | Playground area equipment | PO in estimate
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | PO to be issued
178327 | 19.01.2022 | Router TP link | On line purchase
178328 | 20.01.2022 | 3 way rocker | PO to be issued
178342 | 24.01.2022 | Control panel for pump | PO to be issued
178356 | 01.02.2022 | Bison boards,Langle brackets,Wooden screws | PO to be issued
178360 | 01.02.2022 | False ceiling | PO to be issued
178364 | 02.02.2022 | Wipro LED lights | PO to be issued
178366 | 02.02.2022 | Regal biege | PO to be issued
List of requisitions Where PO/WO is prepared and items have not received at site
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177901 | 07.08.2021 | Urban wood natural | Part material received. Remaining material no stock at Supplier
178112 | 20.10.2021 | Garbage Bin | Part material received. Remaining material no stock at Supplier
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered this week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered this week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered this week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by this week
178144 | 06.11.2021 | MS box pipe | Part material delivered Supplier has to arrange the balance material
178147 | 06.11.2021 | Kitchen unit | Part material delivered, Work under progress
178152 | 08.11.2021 | Urban wood natural & Crema marfil | Part material received remaining material no stock at supplier
178164 | 13.11.2021 | Janata paste | Material available at SSLLP Store delivery by next week
178191 | 23.11.2021 | Glass partition | Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178217 | 06.12.2021 | Roff chemical | Part material received remaining material to be arranged by supplier
178230 | 08.12.2021 | Wall hung rag bolts | Part material received remaining material no stock at supplier
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material delivery in next week
178298 | 06.01.2022 | fishers | Part material received remaining material no stock at supplier
178299 | 06.01.2022 | Pvc false ceiling | Part material received remaining material no stock at supplier
178302 | 07.01.2022 | UPVC windows | Work under progress
178303 | 07.01.2022 | Glass door | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178305 | 08.01.2022 | Paper bundles | Deliverd
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178335 | 22.01.2022 | Cleaning material | Deliverd
178336 | 22.01.2022 | Cleaning material | Deliverd
178337 | 22.01.2022 | Sponges,grout,lappam patti ,etc | Deliverd
178339 | 21.01.2022 | Floor tiles 300mmx300mm | Collect from GMR
178344 | 25.01.2022 | Roff tile chemical | Deliverd
178350 | 28.01.2022 | Mirrors | Deliverd
178357 | 01.02.2022 | Metal box,PVC pipes,tapes,etc., | Deliverd
178358 | 01.02.2022 | Flush plate,wall hung rag bolts | Deliverd
178361 | 02.02.2022 | UPVC windows | Work under progress
178362 | 01.02.2022 | Stationary | Deliverd
178363 | 02.02.2022 | Checkered tiles | Supplier has to arrange the material
178365 | 03.02.2022 | Sprayer | Delivery in next week