## KNM
Prepared by: | Kavitha
Report Date | 27-01-2022
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95032 | 17-01-2022 | UPVC Windows | PO issued, po no-85197
95033 | 17-01-2022 | UPVC Sliding windows | PO issued, po no-85198
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
94942 | 2021-03-11 | Pendrive | online purchase
94990 | 15-12-2021 | Biometric device charger | online purchase
95006 | 27-12-2021 | Labour helmets and ackets | partly delivered, remaining to be collect from ssllp
95008 | 30-12-2021 | Vrtified tiles | Pick up from ssllp
95009 | 30-12-2021 | Travertine carilina | Pick up from ssllp
95015 | 2022-08-01 | tubelight | Pick up from ssllp
95018 | 2021-10-01 | shera clading boards | Follow up with suppleir
95019 | 2022-10-01 | tanbrown granite | Pivk up from SOV
95024 | 2022-10-01 | lights | Follow up with suppleir
95025 | 2022-12-01 | light | Pick up from ssllp
95030 | 17-01-2022 | SS name plates | Follow up with suppleir
95034 | 17-01-2022 | Wipro granite | Follow up with suppleir
95035 | 17-01-2022 | fans | Follow up with suppleir
95036 | 18-01-2021 | Safety material | Pick up from ssllp