## KNM
Prepared by: | Mounika
Report Date | 07.02.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20.07.21 | Solar Module | Supplier will arrange
175467 | 03.01.22 | Tan Brown Granite | Ready with SOV
175472 | 19.01.22 | Nilgiri Trees | Ready with Radhakrishna Supplier
175474 | 25.01.22 | Sanitary | Pick the Material at SSLLP
175475 | 25.01.22 | CP Fittings | Pick the Material at SSLLP
175478 | 29.01.22 | Waste Coupling | Ready with material at Supplier