## VOC LLP
Prepared by: | Mounika
Report Date | 12.02.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186202 | 18.01.22 | Breath Analyzer | Online purchase
186217 | 02.02.22 | Memory card | Online purchase
186219 | 05.02.22 | GI Flat patti | Po to be issue
186190 | 11.01.22 | HDPE Rope | Local Purchase
186211 | 29.01.22 | GI Tower | Po to be issue
186208 | 28.01.22 | WI FI Router | Online purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186171 | 16.12.21 | Yellow Spray Paint | Cancelled
186213 | 31.01.22 | Gunny Bags | Ready With SSLLP