## KNM
Prepared by: | vanajakshi
Report Date | 2022-02-12
Site | Vista Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
180920 | 21.01.2 | Steel Guard's | Sent to MD'S for approval
List of requisitions Where PO/WO is prepared and items have not received at site
180903 | 27.12.21 | Main door lights | Mterial already Delivered
180922 | 1.02.2022 | DR Fixit | Material Delivered