## SOV III
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-02-12
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164173 | 2021-11-22 | FRP Man hole covers | Samples to be receive
164305 | 2021-12-17 | Alaram gong valve | Hold by Waseem
164323 | 2021-12-21 | Led sign boarrd | Clarification required from site
164366 | 2021-12-30 | GI Pipe wrapping material | Po to be issue
164402 | 2022-01-10 | Breath analysys | Online purchased awaiting for delivery
164415 | 2021-01-11 | LED TV | PO 85605
164436 | 2021-01-18 | 1 hp pumps | Rates enquiry
164448 | 2022-01-20 | Steel grey granite | PO 84830
164471 | 2022-01-27 | Duracell batteries | PO 85393
164475 | 2022-01-28 | Tool kit | Local purchase
164476 | 2022-01-28 | Camera | Online purchase
164478 | 2022-01-19 | Ceiling fans | PO 85254
164484 | 2022-01-31 | Steel. | Cancelled
164485 | 2022-01-31 | GI Earthing strip | PO 85279
164486 | 2022-02-02 | Tapes, waterlevel. Line dori etc | PO 82250
164492 | 2022-02-02 | MS Rectangle plate | Local purchase
164498 | 2022-02-02 | HMT Junction box | Po to be issue
164503 | 2022-02-04 | HP laptop charger | Local purchase
164513 | 2022-02-07 | Jointing morter for ACC Blocks | PO 85595
164528 | 2022-02-09 | 2 way angle cock | PO 85490
164530 | 2022-02-11 | Bathroom mirror | PO 85432
164534 | 2022-02-11 | Electrical gloves | PO to be issue
164537 | 2022-02-11 | SS Railing | Cancelled by MD
List of requisitions Where PO/WO is prepared and items have not received at site
163601 | 2021-06-30 | HT Works | Work under process
163704 | 2021-08-07 | ACP Cladding | Work under process
164011 | 2021-10-18 | Busduct material | Work under process
164260 | 2021-12-08 | Goods lift | Under process
164263 | 2021-12-08 | Organic waste converter | Co ordinate with suppplier
164304 | 2021-12-18 | Fire safety equipments | Work under process
164311 | 2021-12-18 | False ceiling work | Work under process
164347 | 2021-12-31 | Pressure switch | Next week delivery
164348 | 2021-12-27 | Vaccum degasser | Work under process
164357 | 2021-12-29 | Al windows | Under fabrication work
164371 | 2021-12-31 | Chiller materials | Work under process
164457 | 2022-01-22 | SS Railing | Work under process
164459 | 2022-01-22 | Mouse | Purchase locally
164482 | 2022-01-31 | Hand pallet truck | Co ordinate with suppplier
164488 | 2022-02-02 | SS Railing | Work under process
164494 | 2022-02-03 | Fire doors | Co ordinate with suppplier
164511 | 2022-02-07 | Wll reclining ladder | Next week delivery
164512 | 2022-02-07 | Gloves | Deliverd
164514 | 2022-02-07 | Frisco grass, Creepers | Deliverd
164518 | 2022-02-08 | MS Round pipes, anchor bolts clamps | Deliverd
164519 | 2022-02-07 | Sand stone lt grey tile | PO issued to Bathstores, co ordinate with supplier
164522 | 2022-02-07 | 1.5 hp ss pump | Co ordinate with suppplier