## VOC LLP
Prepared by: | Mounika
Report Date | 12.02.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186202 | 18.01.22 | Breath Analyzer | Delivered
186217 | 02.02.22 | Memory card | Online purchase
186211 | 29.01.22 | GI Tower | Requisition sent to MD Approval
186208 | 28.01.22 | WI FI Router | Online purchase
186220 | 12.02.22 | Chipping machine | Requisition sent to MD Approval
List of requisitions Where PO/WO is prepared and items have not received at site
186224 | 15.02.22 | Agromesh | Delivered
186221 | 12.02.22 | Welding rods | Ready With SSLLP