## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-02-19
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | Quotes to be received
178301 | 06.01.2022 | Jerry cans | Online purchase
178310 | 11.01.2022 | Playground area equipment | Quotes to be received
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | PO to be issued
178327 | 19.01.2022 | Router TP link | On line purchase
178328 | 20.01.2022 | 3 way rocker | PO to be issued
178342 | 24.01.2022 | Control panel for pump | PO to be issued
178369 | 05.02.2022 | Executive bag | Online purchase
178376 | 07.02.2022 | Laptop | Cancelled by MD
178386 | 12.02.2022 | Bison boards,L angle brackets,Wooden screws | PO 85833, 85842
List of requisitions Where PO/WO is prepared and items have not received at site
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177901 | 07.08.2021 | Urban wood natural | Part material received. Remaining material no stock at Supplier
178112 | 20.10.2021 | Garbage Bin | Part material received. Remaining material no stock at Supplier
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178152 | 08.11.2021 | Urban wood natural & Crema marfil | Part material received remaining material no stock at supplier
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178217 | 06.12.2021 | Roff chemical | Part material received remaining material to be arranged by supplier
178230 | 08.12.2021 | Wall hung rag bolts | Part material received remaining material no stock at supplier
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material delivery in next week
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178350 | 28.01.2022 | Mirrors | Deliverd.
178358 | 01.02.2022 | Flush plate | Deliverd.
178361 | 02.02.2022 | UPVC windows | Work under progress
178366 | 02.02.2022 | Regal biege | Awaiting to receive the stock from Hestia
178372 | 07.02.2022 | Cleaning material | Deliverd.
178373 | 07.02.2022 | Insulation tape,Hacksaw blade | Deliverd.
178377 | 08.02.2022 | DAP | Deliverd.
178381 | 10.02.2022 | Inwall tank | Pick up from SSLLP
178382 | 10.02.2022 | WIPRO garden batten | Deliverd.
178383 | 11.02.2022 | Blue sheets | Deliverd.
178384 | 11.02.2022 | Round square cover | Deliverd.
178387 | 16.02.2022 | CI Gate valve | Deliverd.
178388 | 16.02.2022 | Fan rods, anchor hooks,fan clamps | Collect from Elegant enterprises