## KNM
Prepared by: | Kavitha
Report Date | 24-02-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165576 | 2022-02-11 | Wires | Estimate with MD Sir
165580 | 2022-02-11 | Pressure machine | Enquiry in market
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165460 | 2021-04-09 | Utility tiles | We are arranging for material
165512 | 29-10-2021 | CP material | 95% delivered
165513 | 29-10-2021 | Wash basin pedestal | We are arranging for material
165521 | 15-11-2021 | urban wood light | 50% delivered
165540 | 2021-03-12 | PVC Material | 90% deliverd
165544 | 13-12-2021 | Wires | We are arranging for material
165546 | 14-12-2021 | SS Railing | Contact suplier
165555 | 28-12-2021 | Utility tiles | Next week delivery
165563 | 20-01-2022 | CP Material | Next week delivery
165564 | 20-01-2022 | Sanitary mateial | Next week delivery
165565 | 28-01-2022 | MS gate | Next week delivery
165566 | 28-01-22 | MS gate | Next week delivery
165569 | 29-01-2022 | luppum | 40% delivered Next week delivery
165570 | 29-01-2022 | window grills | We are arranging for material
165571 | 29-01-2022 | MS railing | We are arranging for material
165572 | 31-01-2022 | panel doors | We are arranging for material
165573 | 31-01-2022 | RO plant serving | Contact suplier
165775 | 2022-02-05 | Indigo paint | We are arranging for material
165579 | 2022-02-11 | Gate material | We are arranging for material