## KNM
Prepared by: | Kavitha
Report Date | 18-02-2022
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95039 | 21-01-2022 | Laptop bags | Online purchase
95060 | 2022-08-02 | MS Pipe | PO Issued, PO No-85512
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95006 | 27-12-2021 | Labour helmets | Partly delivered, remaining to be collect from SSLLP
95024 | 2022-12-01 | Lights | Partly delivered, remaining to be collect from Supplier
95032 | 17-01-2022 | UPVC Windows | Follow up with suppleir
95033 | 17-01-2022 | UPVC Sliding doors | Follow up with suppleir
95036 | 18-01-2022 | Safety shoe | Partly delivered, remaining to be collect from SSLLP
95041 | 24-01-2022 | Welspun carpet Tiles | Follow up with suppleir
95052 | 29-01-2022 | Shower head | Partly delivered, remaining to be collect from SSLLP
95057 | 2022-02-05 | PVC External | Partly delivered, remaining to be collect from SSLLP
95059 | 2022-02-08 | Vertified tiles | 85363
95061 | 2022-02-09 | Electrical conductives | pick up from SSLLP
95062 | 2022-02-09 | Electrical conductives | pick up from SSLLP