## KNM
Prepared by: | Kavitha
Report Date | 2022-09-02
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165460 | 2021-04-09 | Utility tiles | Pick from GMR
165512 | 29-10-2021 | CP material | 80% delivered
165513 | 29-10-2021 | Wash basin pedestal | Follow up with suppleir
165521 | 15-11-2021 | urban wood light | 50% delivered
165540 | 2021-03-12 | PVC Material | 70% delivered
165544 | 13-12-2021 | Wires | pick up from ssllp
165546 | 14-12-2021 | SS Railing | Follow up with suppleir
165548 | 18-12-2021 | AL Windows | 80% delivered
165555 | 28-12-2021 | Utility tiles | Pick from GMR
165560 | 13-01-2022 | pavers | 95% delivered
165562 | 20-01-2022 | PVC Material | 70% delivered
165563 | 20-01-2022 | CP Material | pick up from ssllp
165564 | 20-01-2022 | Sanitary mateial | pick up from ssllp
165565 | 28-01-2022 | MS gate | pick up from ssllp
165566 | 28-01-22 | MS gate | pick up from ssllp
165567 | 28-01-2022 | pavres | Follow up with suppleir
165569 | 29-01-2022 | luppum | pick up from ssllp
165570 | 29-01-2022 | window grills | pick up from ssllp
165571 | 29-01-2022 | MS railing | Follow up with suppleir
165572 | 31-01-2022 | panel doors | Follow up with suppleir
165573 | 31-01-2022 | RO plant serving | Follow up with suppleir
165574 | 31-01-2022 | pappum | pick up from ssllp