## NE
Prepared by: | Mounika
Report Date | 28.02.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20.07.21 | Solar Module | Supplier will arrange
175478 | 29.01.22 | Waste Coupling | Ready with material at Supplier
175484 | 18.02.22 | Cylindricals locks | Collect from SSLLP
175486 | 22.02.22 | Sanitary | Collect from SSLLP
175487 | 22.02.22 | CP Fittings | Collect from SSLLP
s