## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-02-26
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164173 | 2021-11-22 | FRP Manholes | Orderd samples in SSLLP once approve from MD will place an orders
164305 | 2021-12-17 | Alaram gong valve | Cancelled by Waseem
164323 | 2021-12-21 | Led sign board | Cancelled due to specification are incorrect
164366 | 2022-01-10 | GI Pipe wrapping material | PO 85850
164402 | 2022-01-10 | Brethe analasys | Online purchased awaiting for delivery
164436 | 2022-01-18 | 1 hp pump, with suitable pipe, diesel hand pump | Requisition sent for mds approval
164492 | 2022-02-02 | MS Rectanguler plate | Local purchase by raghu, remove from here
164503 | 2022-02-04 | Laptop charger | Follow up with suneel sys admin
164545 | 2022-02-12 | MS Drums | Local purchase by raghu, remove from here
164553 | 2022-02-15 | MS Round plates | Locally purchase by Narendar and deliverd at Site remove from here
164557 | 2022-02-16 | Cafeterial material | PO 85784
164568 | 2022-02-16 | Hand drayer machione, Bin, Tissue paper | PO to be issue
165750 | 2022-02-17 | Checkrd plates | Estimate is with MD for approval
164580 | 2022-02-18 | MS Sandwich panel | PO 86069
164593 | 2022-02-19 | SS Railing | PO 85818
164606 | 2022-02-21 | Thermo wheel | Awaiting for quotes to be receive
164608 | 2022-02-22 | Rest room cubicals | PO to be issue
164609 | 2022-02-22 | Caution tapes | PO to be issue
164612 | 2022-02-23 | MS Ladder | PO to be issue
164614 | 2022-02-23 | Dummy ms ba class round pipes | PO 86002, 85948
List of requisitions Where PO/WO is prepared and items have not received at site
163601 | 2021-06-30 | HT Works | Work under progress
163704 | 2021-08-07 | ACP cladding | Work under progress
164011 | 2021-12-08 | Busduct material | Work under progress
164260 | 2021-12-08 | Goods lift | Work under progress
164263 | 2021-12-08 | Organic waste converter | Deliverd
164304 | 2021-12-18 | Fire fighting system | Work under progress
164311 | 2021-12-18 | False ceiling work | Work under progress
164348 | 2021-12-27 | Vacuum degasser | Deliverd
164357 | 2021-12-29 | Al windows | Work under progress
164557 | 2022-02-22 | Cafeteria material | PO issued awaiting to receive the material
164488 | 2022-02-02 | SS Railing | Work under progress
164494 | 2022-02-03 | Fire doors | Co ordinate with supplier for delivery
164512 | 2022-02-07 | Gloves | Deliverd
164514 | 2022-02-07 | IV Creepers | Deliverd
164519 | 2022-02-07 | Sand stote light grey | PO issued awaiting to receive the material
164529 | 2022-02-09 | Eco drain pipe | Pick up from Praful sanitary
164530 | 2022-02-09 | Bathroom mirrors | Pick up from Abhinav Photo frames
164535 | 2022-02-11 | First aid kit | Pick up from SSLLP
164551 | 2022-02-14 | Eco drain pipe | Deliverd
164575 | 2022-02-17 | RO Dosing chemicals | Co ordinate with supplier for delivery
164583 | 2022-02-17 | Silicon gel tubes | Local purchase
164594 | 2022-02-19 | Safety shoes | pick up from ssllp
164596 | 2022-02-19 | Steel sing boards | Work under progress
164599 | 2022-02-21 | cutting wheels, tester, cutting plair | Co ordinate with supplier for delivery
164595 | 2022-02-21 | Texture | Co ordinate with supplier for delivery