## KNM
Prepared by: | Kavitha
Report Date | 2022-03-03
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165576 | 2022-02-11 | Wires | Cancelled by MD Sir
165577 | 2022-02-11 | Wall maounted urinal | PO Issued-PO No-85721
165580 | 2022-02-11 | Pressure Mechine | Enquiry in market
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165460 | 2021-04-09 | Utility tiles | 85% deliverd
165512 | 29-10-2021 | CP material | 95% delivered
165513 | 29-10-2021 | Wash basin pedestal | 95% delivered We are arranging remaining material
165540 | 2021-03-12 | PVC Material | 90% deliverd
165544 | 13-12-2021 | Wires | We are arranging for material
165563 | 20-01-2022 | CP Material | Next week delivery
165564 | 20-01-2022 | Sanitary mateial | Next week delivery
165570 | 29-01-2022 | window grills | We are arranging for material
165572 | 31-01-2022 | panel doors | We are arranging for material
165579 | 2022-02-11 | Gate material | Next week delivery
165577 | 2022-02-11 | Wash basin pedestal | 95% delivered We are arranging remaining material