## KNM
Prepared by: | Kavitha
Report Date | 2022-03-02
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95039 | 21-01-2022 | Laptop bags | Online purchase
95066 | 22-02-2022 | Drilling machine | PO issued-PO no-85978
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95024 | 2022-12-01 | Lights | Partly delivered, remaining to be collect from Supplier
95032 | 17-01-2022 | UPVC Windows | Contact supplier
95033 | 17-01-2022 | UPVC Sliding doors | Contact supplier
95036 | 18-01-2022 | Safety shoe | Partly delivered, remaining to be collect from SSLLP
95061 | 2022-02-09 | Electrical conductives | pick up from SSLLP
95065 | 22-02-2022 | Stationery | pick up from SSLLP