## VOC LLP
Prepared by: | Mounika
Report Date | 05.03.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186220 | 12.02.22 | Chipping machine | Requisition sent to MD Approval
186217 | 02.02.22 | Memory card | Online purchase
186211 | 29.01.22 | GI Tower | Requisition sent to MD Approval
186208 | 28.01.22 | WI FI Router | Online purchase
186230 | 19.02.22 | Land line phone | Online purchase
186233 | 19.02.22 | Tea Flask | Local Purchase
186233 | 19.02.22 | Metna | Local Purchase
List of requisitions Where PO/WO is prepared and items have not received at site
186226 | 18.02.22 | L-Angle | Ready With supplier
186232 | 19.02.22 | Spray Paints | Delivered