## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-03-05
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178270 | 24.2.2021 | EPDM flooring | Quotes to be received
178301 | 06.01.2022 | Jerry cans | Cancel the requisition
178310 | 11.01.2022 | Playground area equipment | Under negotiation
178314 | 11.01.2022 | SS Railing | PO to be issued
178316 | 11.01.2022 | Sensor type urinal,Urinal waster coupling | PO to be issued
178327 | 19.01.2022 | Router TP link | On line purchase
178328 | 20.01.2022 | 3 way rocker | Under negotiation
178342 | 24.01.2022 | Control panel for pump | PO to be issued
178369 | 05.02.2022 | Executive bag | Online purchase
178397 | 21.02.2022 | Sliding windows | PO to be issued
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177498 | 19.03.2021 | Stainless steel sink | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
177901 | 07.08.2021 | Urban wood natural | Part material received. Remaining material no stock at Supplier
178112 | 20.10.2021 | Garbage Bin | Deliverd
178122 | 26.10.2021 | UPVC Windows | Work under progress
178125 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178126 | 29.10.2021 | Wall mixtures | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178127 | 29.10.2021 | Wall hung WC | Bulk order, Part material delivered, remaining material available at supplier will be delivered next week.
178128 | 29.10.2021 | Wall hung WC | Bulk order, Supplier has the material, delivery by next week
178152 | 08.11.2021 | Urban wood natural & Crema marfil | Part material received remaining material no stock at supplier
178191 | 23.11.2021 | Glass partition | Part material delivered, Work under progress
178208 | 30.11.2021 | UPVC Windows | Work under progress
178217 | 06.12.2021 | Roff chemical | Deliverd
178230 | 08.12.2021 | Wall hung rag bolts | Deliverd
178268 | 24.12.2021 | DB Board single phase | Part material received remaining material delivery in next week
178302 | 07.01.2022 | UPVC windows | Work under progress
178304 | 07.01.2022 | UPVC windows | Work under progress
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Work under progress
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Work under progress
178366 | 02.02.2022 | Regal biege | Supplier arranging material
178377 | 08.02.2022 | DAP | Delivery in next week
178381 | 10.02.2022 | Inwall tank | Part material deliverd balance to be deliverd
178386 | 12.02.2022 | L angle brackets | Delivery in next week
178389 | 17.02.2022 | Vent cover | Deliverd
178390 | 18.02.2022 | Emery paper | Deliverd
178393 | 22.02.2022 | EWC P TRAP | Deliverd
178394 | 21.02.2022 | Traffic cones | Deliverd
178396 | 21.02.2022 | Kitchenunit | Work under progress
178399 | 23.02.22 | Pvc flase ceiling sheets | Work under progress
178400 | 25.02.22 | Plants | Co ordinate with supplier for delivery
178401 | 26.02.22 | Roff chemicals | Deliverd