## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-03-05
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164173 | 2021-11-22 | FRP Manholes | Orderd samples in SSLLP once approve from MD will place an orders
164402 | 2022-01-10 | Brethe analasys | Online purchased awaiting for delivery
164436 | 2022-01-18 | 1 hp pump, with suitable pipe, diesel hand pump | Requisition sent for mds approval
164492 | 2022-02-02 | MS Rectanguler plate | Local purchase by raghu, remove from here
164545 | 2022-02-12 | MS Drums | Local purchase by raghu, remove from here
164568 | 2022-02-16 | Hand drayer machione, Bin, Tissue paper | PO to be issue
164612 | 2022-02-23 | MS Ladder | PO to be issue
164625 | 2022-02-25 | Timer for Lights | Cancelled
164628 | 2022-02-25 | PVC Glands, Nail clams | Cancelled
164631 | 2022-02-24 | Flexible cable, single socket plugs | Cancelled
164632 | 2022-02-24 | Horizontal centrifugal motor guard | Requisition sent for mds approval
164633 | 2022-02-24 | PVC Cable glands | Cancelled
164636 | 2022-02-26 | Foam board 5 mm | Requisition not received
164638 | 2022-02-26 | Self screws | PO to be issue
164640 | 2022-02-26 | office table, revolveing chair, storage | Estimate to be prepare
164648 | 2022-03-03 | Gun grey paint | PO 86088
164649 | 2022-03-03 | CC Cameras, memory cards | Online purchased awaiting for delivery
164650 | 2022-03-03 | Solar panel | Quote to be receive
List of requisitions Where PO/WO is prepared and items have not received at site
163601 | 2021-06-30 | HT Works | Work under progress
163704 | 2021-08-07 | ACP cladding | Work under progress
164011 | 2021-12-08 | Busduct material | Work under progress
164260 | 2021-12-08 | Goods lift | Work under progress
164304 | 2021-12-18 | Fire fighting system | Work under progress
164311 | 2021-12-18 | False ceiling work | Work under progress
164357 | 2021-12-29 | Al windows | Work under progress
164488 | 2022-02-02 | SS Railing | Work under progress
164519 | 2022-02-07 | Sand stote light grey | PO issued awaiting to receive the material
164530 | 2022-02-09 | Bathroom mirrors | Pick up from Abhinav Photo frames
164534 | 2022-01-11 | Electrical gloves | PiPick up from supplier
164541 | 2022-02-11 | B class pipes | Pick up from supplier
164570 | 2022-02-17 | Checkred plates | Pick up from supplier
164580 | 2022-02-18 | MS Sandwich panel | Pick up from supplier
164585 | 2022-02-18 | Wash basin | Pick up from supplier
164593 | 2022-02-19 | SS Railing | Pick up from supplier
164605 | 2022-02-22 | 40 mm square pipe | Pick up from supplier
164611 | 2022-02-23 | MS Requatanguler plates | Pick up from supplier
164614 | 2022-02-23 | Dummy flange | Pick up from supplier
164639 | 2022-02-26 | SS Railing | Pick up from supplier
164647 | 2022-03-03 | Shabhad stone | Pick up from supplier