## NE
Prepared by: | Mounika
Report Date | 14.03.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
175488 | 26.02.22 | CC Cameras | Po to be issue
175490 | 05.03.22 | Desk Double cot | Estimate to be prepare
17491 | 05.03.22 | Double cot bed | Estimate to be prepare
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20.07.21 | Solar Module | Supplier will arrange
175492 | 07.03.22 | Sliding windows | Collect from SSLLP
175493 | 07.03.22 | Window Grills | Collect from SSLLP
s